## Work Plan
AFRICA CENTRES OF EXCELLENCE (ACE)
XYZ UNIVERSITY WORK PLAN (JANUARY - DECEMBER 2017)
| CMP XX | [9 empty] | Year 2017
Activity No | COMPONENT | ACTIVITIES | ACTIVITY CLASSIFICATION | OBJECTIVE | JUSTIFICATION | OUTPUT | ESTIMATED BUDGET ($) |  |  | RESPONSIBLE UNIT | January - December 2017
[7 empty] | Main | Partners | Total |  | January | Febrary | March | April | May | June | July | August | September | October | November | December
Component 1: Strengthening Africa Centers of Excellence
DLR 1.1 | Running of CEADESE Office | Day-day running CEADESE Office | Operating cost | To acquire and install small office equipment, toners, cartridge, sevicing of equipment, etc | Requirement for the office to function | Efficiency | 18750 |  |  | Director
|  | Procurement of Stationery and consumables | Operating cost | To acquire printing papers, pens, pencils, files, letterheads, etc. | Required for printing documents, for meetings, keeping records, etc. | Records | 3125 |  |  | Director
|  | Maintainning Project Vehicle | Operating cost | For fueling and servicing of project vehicles | For students trips, for errands, farms works, etc. | Efficiency | 10000 |  |  | CEADESE Admin Officer
|  | Developing Implementation Plans, Budget Procurement plan | Operating cost | Required for the several meetings to formulate the 2018 plans. | payment of meeting expenses | Production of 2017 Implementation, Work and Procurement Plans | 3125 |  |  | Director
|  | Signing MoUs | Operating cost | Required for furging partnerships | Expenses on travels, and production of MOUs | MOUs signed | 50000 |  |  | Director
|  | Adverts / contacts | Operating cost | Required for placement of advertisements, communications. | CEADESE information, telephone bills, internet data. | number of contacts, and advertisements | 10000 |  |  | Director
|  | Operational cost |  |  |  |  | 3125
DLR 1.2 | Coordination of Meetings | Coordinating CEADESE Meetings | Operation cost | Required to prepare for the various Centre meetings | Expenses for refreshments, payment of mileage for invited participants | Meeting records | 25000 |  |  | CEADESE Admin Officer
|  | Hosting stakeholder’s workshops | Operating cost | Required for holding National stakeholders workshop especially partners. | Expenses for refreshments, payment of mileage for invited participants | One meeting in 2007. Record of meeting. | 10000 |  |  | Director
DLR 1.3 | Attendance at World Bank/ AAU Workshops | Attending World Bank meetings and Workshops | Operating cost and Trainings | Required for attending World Bank and AAU organised workshops. | Expenses for travels, estacodes, DTA. | Progress reports of achivements presented at workshops. | 81250 |  |  | Director
DLR 1.4 | Technical & Management Trainings | Trainings (Management Faculty and Technologists) | Management Training/Staff Skill enhancement | Required to train the management team of the Centre in Project management nationally and internationally, train faculty to enhance teaching and research skills, and to enhance the analytical skills of technologist. | Expenses for course fee, travels, estacodes, DTA for Centre Leader, deputy, M&E, Accountant, Audit, Procurement, some faculty. 1) 6 Members of CEADESE Management Team; 2) 6 CEADESE Programme Leaders; 3) Relevant Deans | Number of officers to be trained (Centre Officers, University Management Officers, Technologists, College Deans, Programme Leaders). Some faculty Certificates of attendance. | 300000 |  |  | Director
DLR 1.5 | Travels (Local & International) | Travels (Local & International) | Operation cost | Travels by officers and faculty on official assignments | Expenses incurred on travels, mileage, Estacodes, DTA. | Meeting records and reports | 50000 |  |  | Accountant
DLR 1.6 | Running of CEADESE website | Running of CEADESE website | Operating cost | 1) Web hosting and updating | Expenses on web hosting by ICT Unit of University | For transparancy | 1000 |  |  | Information Officer
|  |  |  | 2)Subscription to internet and online journals |  |  | 180000
DLR 1.7 | Facilitation of FUNAAB Industrial Relations | Facilitation of FUNAAB Industrial Relations | Internships | Required by Centre's Industrial Liaison officers. | Expenses on search for industrial internship placements | Placement of Masters and Phd students in industry and partners establishments | 5000 |  |  | Industry Liaison Officers
DLR 1.8 | Internal & External M & E | Project Monitoring and Evaluation | Operating cost | Required for the monitoring activities of M&E | Expenses incurred. | Reports | 5000 |  |  | M&E Officer
DLR 1.9 | Facilitation of FUNAAB Safeguard Office | Facilitation of FUNAAB Safeguard Office | Operation cost | Required for the activities of the Safeguard unit of the Centre Refresher courses for safeguard officer Regular training of workers on occupational safegaurd | Expenses incurred meetings, travels, and reporting | Reports to WB | 6000 |  |  | Safeguard Officer
DLR 1.10 | Facilitation of CEADESE Communication office | Facilitation of CEADESE Communication office | Operating cost | Required by the Communications officer Projecting image and activities of the Centre | Expenses on communication needs, photography, liaison with press and AAU | Reporting Centre activities in press and bulletins | 10000 |  |  | Communications Officer
DLR 2.1 | Runing Short-term courses for Students | Teaching Materials and softwares | Goods Procurement | Required for procurement of teaching | Expenses on procuring course materials for short term courses and workshops | Short terms courses delivered and number of participants. | 10000 |  |  | Deputy Director
|  | Admission advertisements | Operating | Required for advertising for participants in short term courses. | Cost of advertisement placement in newspapers. | Hard copies of advertisements and number of respondents. | 5000 |  |  | Director
|  | Recruitment of Resource Persons for workshops | Operating cost | Required for delivery of lectures and demonstrations of experience | To inpact knowledge and experience | Number of resource persons engaged and paid. Number of trainees. | 5000 |  |  | Accountant
|  | Hosting workshops | Training | Required for impacting practical knowledge. | For additional practical knowledge to for students and stakeholders in agriculture. | Number of workshops held and participants. | 18050 |  |  | Accountant
|  | Procurement of travels, accommodation, honoraria for facilitators | Operating cost | Required as incentive to attract quality facilitors and resource persons | Required as incentive to attract quality facilitors and resource persons | Payment vouchers, travel tickets, boarding passes. | 31250 |  |  | Accountant
|  | Publication of workshop reports | Training | Required for the dissemination of workshop activities | References materials for students and stakeholders | Hard copies of publications | 5000
DLR 2.2 | Running Masters Students Degree Courses | Running language course | Operating cost | For teaching English and French languages | This is to enhance the english of francophone students and to attract regional students from non english speaking countries. | Number of students taught. | 1000 |  |  | M & E Officer
|  | Revision of curricula | Operating cost | Required for yearly updating of teaching curricula |  | Revised curricula, number of courses revised. | 1000
|  | Lectures by adjunct/ part time lecturers/ visiting professors | Operating cost | Lecture delivery throught the year and students research supervision |  | Number lecturers, students. | 25000
|  | Operational Cost |  | For students travels, field trips, attendance of conferences and workshops. | To enhance knowledge, networking, presentation of research works at conferences. | Number of students that benefitted, presentations and payment records. | 25562
|  | Placement of Advertisements for admission | Operating cost | For the recruitment of quality candidates |  | Number of subscriptions and admited candidates, newspaper publications | 2500
|  | Procurement of Course materials | Operating cost | Required for lecture delivery |  | Procurement records | 1000
|  | Procurement of Stationery | Operating cost | For students and lecturers use for photocopies. |  | Procurement records | 1000
|  | Examinations and invigilations | Operating cost | To be conducted at the end of each semester | To test the comprehension of the course by students and for grading | Examination records | 1000
|  | Scholarship awards | Operating cost | To award various grades of scholarships for outstanding candidates | To attract good students and to attract regional students from poor countries. | Number of awards and cost. | 18438
DLR 2.3 | Running PhD Degree Courses | Running language courses | Operating cost | For teaching English and French languages | This is to enhance the english of francophone students and to attract regional students from non english speaking countries. | Number of students taught. | 1000 |  |  | M & E Officer
|  | Revision of curricula | Operating cost | Required for yearly updating of teaching curricula |  | Revised curricula, number of courses revised. | 1000
|  | Lectures by regular, Adjunct/ part time lecturers/ visiting professors | Operating cost | Lecture delivery throught the year and students research supervision |  | Number of students taught and supervised. | 25000
|  | Operational Cost | Operating cost | For students travels, field trips, attendance of conferences and workshops. | To enhance knowledge, networking, presentation of research works at conferences. | Number of students that benefitted, presentations and payment records. | 25562
|  | Placement of Advertisements for admission | Operating cost | For the recruitment of quality candidates |  | Number of subscriptions and admited candidates, newspaper publications | 2500
|  | Procurement of Course materials | Operating cost | Required for lecture delivery |  | Procurement records | 1000
|  | Procurement of Stationery | Opertaing cost | For students and lecturers use for photocopies. |  | Procurement records | 1000
|  | Exams and invigilation | Operating cost | To be conducted at the end of each semester | To test the comprehension of the course by students and for grading | Examination records | 1000
|  | Scholarship awards | Operating cost | To award various grades of scholarships for outstanding candidates | To attract good students and to attract regional students from poor countries. | Number of awards and cost.
DLR 2.4 | Outreach “periods” (faculty and students) | Travel and Maintenance expenses by M.AgSE Students | Operating cost/Training/Internship | Required to meet students expenses during internships or certified training in other laboratories. | For transports fares, living expenses | Record of internship placements and payment vouchers. | 20000 |  |  | Deputy Director
|  | Travel and Maintenance expenses for PhD.AgSE Students | Operating cost/Training/Internship | Required to meet students expenses during internships or certified training in other laboratories. | For transports fares, living expenses | Record of internship placements and payment vouchers. | 20000
|  | Travel and Supervision expenses for Faculty | Operating cost/Internships/Training | Required for faculty expenses for internship supervision, Training of faculty in other institutions or laboratories. | Faculty need to visit interns at their placement industries/collaborating institutions. | Number of faculty involved and evidence of training evidence. Workshop certificates. | 25000
|  | Faculty Outreach | Operation cost. | For community Service, collaborative research and skill acquisition | Needed for service to industry and knowledge dissemination and acquisition | Number of faculty on outreach in other establishments. | 60000
DLR 2.5 | Accreditation | [8 empty] | M & E Officer
| Gap assessment certified/self evaluation | Procurement of Stationery | Operating cost | Production of documents required for assessment and remuneration of assessors |  |  | 3125
| International Accreditation | International Accreditation | Operating cost | To invite AQAS to conduct international accreditation of all the Centre programmes | For international recognision of the Centre programmes. | Certificate of accreditation
DLR 2.6 | Number of papers published in Internationally recognized and Peer-Review Journal | Research and Research support | Operating cost | To conduct standand research that would be published in recognised journals and adoptable findings. | Expenses for executing standard research work to generate publications and publication charges. | Number of students thesis, publications and adoptable research findings | 162500 |  |  | M & E Officer
|  | Research theses/dissertations preparation for postgraduate School approval for 45 students | Operating Cost | Required for assisting final thesis binding | Expenses on thesis preparation | Number of theses completed | 25000
|  | Publications | Operating cost | Required for publishing research findings | Expenses on page charges | Number of papers published in high impact journals | 50000
DLR 2.7 | Externally generated Revenue | Activities for generating External Revenue | Operating cost | Fund raising through farm products production, organizing workshops, solicitations, preparation of grants, travels for fund raising |  | Record of amount generated | 100000 |  |  | Finance Officer
DLR 2.8 | Meeting milestones for improved learning and research environment specified in the Performance and Funding Contracts
|  | Milestone 2 | Civil Works | Procurement | Refurbishment of Students Hostel and Computer Laboratory for conducive accommodation and learning environment | Amenities provided/Evidence of Structure refurbished and verified by Procurement consultants | 400000
|  | Milestone 3 | Laboratory Equipment and Consumables Purchased | For the procurement of research equipment and consumables for the conduct of standard and publishable research works. | For conducting standard publishable research works by students and faculty | All equipment and consumables listed on approved procurement plan | 400000
|  | Milestone 4 | Establishment of Research Core Facilities | Procurement | This is to improve research buildings such as animal houses and plant production facilities to international standards including students hostels, classrooms and laboratories. | Upgrade 7 research research facilities (buildings housing animals and equipment) | 400000
DLR 3.1 | Timely withdrawal application supported by financial reporting for the ACE account for the period | Running upgraded accounting system | Operating cost | Updating and upgrading of accounting packages. Servicing | This is required to keep our system up to date and engage the provider. This is to enhance timely submission of accounting reports | Record of submitted reports. | 5000 |  |  | Finanvce Officer
|  | Training of financial Officer in World Bank guidelines and fiduciary methods | Training | Centre officials to go on regular training to update skill on fiduciary methods as organised bu AAU/WB/NUC or by independent trainers. | For updating skill | Number of trainings and evidence of attendance. | 10000
DLR 3.2 | Functioning University audit Committee under the university council | Meetings (audit committees) | Operating Cost | Audit committee meeting on quarterly basis for consideration of internal audit reports and annual external audit report. | Required for fund disbursement | Reports | 2000 |  |  | Chairman of Audit Committee
|  | Operational Cost | Operating Cost | Cost for holding meetings |  | Vouchers and minutes | 1000
|  | Training | Training | Audit committee to receive training to understand and enhance duties | To enhance duties | Certificate of training | 10000
DLR 3.3 | Functioning internal audit unit for the university | Internal auditing | Operating Cost | Auditing of all payments and procurements is mandatory. Quarterly reports for presentation to WB | Mandatory | Reports submitted and on website | 3000 |  |  | Internal Afficer Officer
|  | External auditing accounts | Consultancy | Annual external audit to be conducted | Mandatory | Report submitted and displayed on website | 7500
DLR 3.4 | Web Transparency on Financial management (web-access to audit reports,interim financial reports, budgets and annual work plan) | Display of all Reports on website | Operating Cost | To demonstrate financial transparency, all reports and finantial audit to be displayed on Centre website | Mandatory | Disclosures on website | 25000 |  |  | Information Officer
DLR 4.1
DLR 4.2 | Timeliness of procurement progress | Production of procurement manual | Operating cost | Procurement manual production. |  | Copies | 1000 |  |  | Procurement Officer
|  | Producing bid documents | Operating cost | Production of bid documents |  | Copies | 1000
|  | Bids advertisement | Operating Cost | Advertisements in national newspapers and on website |  |  | 2000
|  | Bid opening | Operating Cost | Public bid openning |  | copies and minutes | 1250
|  | Bids Evaluation | Operating Cost |  |  | minutes | 1250
|  | Operational Cost | Operating Cost | Procurement office management |  | records | 2150
|  | Training | Training | Training of procurement officer and staff |  | Certificate of training | 10000
Implementation Committee
|  | Total |  |  |  |  | 2728012

## Procurement Plan Goods
COUNTRY: NIGERIA
PROJECT: P126974 (AFRICA HIGHER EDUCATION CENTRES OF EXCELLENCE PROJECT)
Loan No: 023
NAME OF INSTITUTION: FEDERAL UNIVERSITY OF AGRICULTURE, ABEOKUTA ( CENTRE OF EXCELLENCE IN AGRICULTURAL DEVELOPMENT AND SUSTAINABLE ENVIRONMENT)
GOODS | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
S/NO. | Description* | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
| Norm Duration of Proc Steps |  |  |  |  | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
GOODS
| RESEARCH/FARM/LABORATORY EQUIPMENT |  | 1
| Hydrometer Analysis Set, Speedy 2000 Moisture Tester, Speedy 2000 Moisture Tester, Vacuum sealer, Differential Scanning Calorimeter, Proximate Analyser, Pregnancy Detector, Steel metabolic cage, Force Draught Oven, Artificial Insemination, Liquid Nitrogen , Liquid Nitrogen Tank, Serum Analyzer and HPLC & gas Chromatography columns and etc |  |  | 75000 | NCB | Postqualification | Post review | Plan | N/A | N/A | N/A | 15/02/16 | 30/03/16 | 28/04/16 | N/A | Plan | 75000 | 16/05/16 |  | 06./06/16 | N/A | 10/06/16 | 09/08/16
[8 empty] | Actual | N/A | N/A | N/A | 31/03/16 | 05/05/16 | 29/07/16 | N/A | Actual |  | 28/12/16 |  | 05/01/17 | N/A | 30/01/17 | 03/04/17
| RESEARCH/FARM/LABORATORY EQUIPMENT |  | 2
| Vacuum fryer, Weighbridge, Feed mixer, Feeding troughs and drinkers, Incubator etc |  |  | 55000 | NCB | Postqualification | Post review | Plan | N/A | N/A | N/A | 15/02/16 | 30/03/16 | 28/04/16 | N/A | Plan | 55000 | 16/05/16 |  | 06./06/16 | N/A | 10/06/16 | 09/08/16
[8 empty] | Actual | N/A | N/A | N/A | 31/03/16 | 05/05/16 | 29/07/16 | N/A | Actual |  | 28/12/16 |  | 05/01/17 | N/A | 30/01/17 | 03/04/17
| RESEARCH/FARM/LABORATORY EQUIPMENT |  | 3
1 | Tractor with implements |  |  | 60000 | NS | Postqualification | Post review | Plan | N/A | N/A | N/A | 27/02/17 | 10/04/17 | 08/05/17 | N/A | Plan | 60000 | 05/06/17 |  | 28/06/17 | N/A | 05/07/17 | 04/09/17
[8 empty] | Actual | N/A | N/A | N/A |  |  |  | N/A | Actual |  |  |  |  | N/A
2 | Procurement of Power sources |  |  | 30000 | NS | Postqualification | Post review | Plan | N/A | N/A | N/A | 15/02/16 | 30/03/16 | 28/04/16 | N/A | Plan | 30000 | 16/05/16 |  | 06./06/16 | N/A | 10/06/16 | 09/08/16
[8 empty] | Actual | N/A | N/A | N/A | 31/03/16 | 05/05/16 | 29/07/16 | N/A | Actual |  | 28/12/16 |  | 05/01/17 | N/A | 30/01/17 | 03/04/17
3 | Procurement of (1) one Project Vehicle (Already Purchased) |  |  | 42500 | NS | Postqualification | Post review | Plan | N/A | N/A | N/A | 15/02/16 | 30/03/16 | 28/04/16 | N/A | Plan | 42500 | 16/05/16 |  | 06./06/16 | N/A | 10/06/16 | 09/08/16
[8 empty] | Actual | N/A | N/A | N/A | 26/11/15 | 10/12/15 | 22/12/15 | N/A | Actual | 23,800.00 | 29/03/16 |  | 29/03/16 | N/A | 29/03/16 | 06/04/16
| SUB-TOTAL |  |  | 220000 | [12 empty] | 220000
| Fill gray cells only! |  |  | EXCHANGE RATE: ₦150= U.S. $1.00
CONSUMABLES
| EXPERIMENTAL CONSUMABLES |  | 1
1 | Procurement of animal feeds, Pasture Seeds, Silage inorculants and Germplasm acquisition and etc |  |  | 50000 | DIRECT PROCUREMENT | Postqualification | Post review | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 50000 | 16/05/17 |  | 06/06/17 | N/A | 10/07/17 | 11/09/17
[8 empty] | Actual | [7 empty] | Actual |  |  |  |  | N/A
2 | Experimental Poultry Birds, Collection of 1000 fertile eggs, WAD Goat, kalahari Bucks and etc |  |  | 100000 | DIRECT PROCUREMENT | Postqualification | Post review | Plan | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Plan | 100000 | 16/05/17 |  | 06/06/17 | N/A | 10/07/17 | 11/09/17
[8 empty] | Actual | [7 empty] | Actual |  |  |  |  | N/A
(Itemsd 1& 2 are to be procured from the University and other Project Planners who are experts in the fields. The goods are to be procured as needed.)
| RESEARCH CONSUMABLES |  | 2
| Lab kits for analysis , field kits & Milk composition Analysis Consumables etc. |  |  | 30000 | NCB | Postqualification | Post review | Plan | N/A | N/A | N/A | 15/02/16 | 30/03/16 | 28/04/16 | N/A | Plan | 30000 | 16/05/16 |  | 06./06/16 | N/A | 10/06/16 | 09/08/16
[8 empty] | Actual | N/A | N/A | N/A | 31/03/16 | 05/05/16 | 29/07/16 | N/A | Actual |  | 28/12/16 |  | 05/01/17 | N/A | 30/01/17 | 03/04/17
| SUB-TOTAL |  |  | 180000 | [12 empty] | 180000
| TEACHING AND MULTIMEDIA EQUIPMENT |  | 1
| Supply of Multimedia Facilities, Computer Accessories & Software |  |  | 220000 | NCB | Postqualification | Post review | Plan | N/A | N/A | N/A | 15/02/16 | 30/03/16 | 28/04/16 | N/A | Plan | 220000 | 16/05/16 |  | 06./06/16 | N/A | 10/06/16 | 09/08/16
[8 empty] | Actual | N/A | N/A | N/A | 31/03/16 | 05/05/16 | 29/07/16 | N/A | Actual |  | 28/12/16 |  | 05/01/17 | N/A | 30/01/17 | 03/04/17
| Furnishing of Computer Laboratory |  |  | 120000 | NS | Postqualification | Post review | Plan | N/A | N/A | N/A | 27/02/17 | 10/04/17 | 08/05/17 | N/A | Plan | 120000 | 05/06/17 |  | 28/06/17 | N/A | 05/07/17 | 04/09/17
[8 empty] | Actual | N/A | N/A | N/A |  |  |  | N/A | Actual
| TEACHING AND MULTIMEDIA EQUIPMENT |  | 2
| Library Books & Journal |  |  | 80000 | NS | Postqualification | Post review | Plan | N/A | N/A | N/A | 15/08/16 | 05/09/16 | 26/09/16 | N/A | Plan | 80000 | 03/10/16 |  | 24/10/16 | N/A | 31/10/16 | 30/12/16
[8 empty] | Actual | N/A | N/A | N/A | 15/08/16 | 29/08/16 | 31/08/16 | N/A | Actual |  | 28/12/16 |  | 05/01/17 | N/A | 30/01/17 | 03/04/17
| SUB-TOTAL |  |  | 420000 | [12 empty] | 420000
| GRAND TOTAL |  |  | 820000 | [12 empty] | 820000

## Procurement Plan Consultancy
COUNTRY: NIGERIA
PROJECT: AFRICA CENTRES OF EXCELLENCE
CREDIT NO:
NAME OF INSTITUTION: NATIONAL UNIVERSITIES COMMISSION (NUC)
For Contracts under projects approved before the May 2002 Guidelines
|  |  | If Post-Review, No-objection Dates are not needed | [5 empty] | Request for EOI (where required)
CONSULTANCY |  |  | Contract Type |  |  |  | Preparation Request for Proposals |  |  |  | Short List |  |  | Consultant Proposals |  | Proposal Evaluation and Negotiation for Projects after May 2002 Technical (T) & Financial (F) and Negotions (N) | [5 empty] | Draft Contract |  | Contract Finalization |  |  |  |  | Contract Implementation
S/No. | DESCRIPTION OF ASSIGNMENT | Selection Method | Lumpsum or Time-Based | Estimated Amount in US$ '000 | Prior/Post Review | Plan vs. Actual | Prep & Submission by Ex Ag | No-objection Date | On-line UNDB Gateway Nat Press | Lead-time before shortlist | Submission Date | No-objection Date | Plan vs. Actual | Invitation Date | Submission/ Opening Date | Submission Evaluation Report (T) | No-objection Evaluation Report (T) | Opening Financial Proposals | Preparation Eval Report (T) (F) | Negotiations (N) | Plan vs. Actual | Submission Date | No-objection Date | Contract Amount in US$ '000 | Contract Award | Date Contract Advert | Contract Signature | Plan vs. Actual | Mobilization Advance Payment | Draft Report | Final Report | Final Cost US$ '000
[6 empty] | Plan | 3 - 6 wks | 1 - 2 wks | 1 - 1.5 wks | 2 wks |  | 1 - 2 wks | Plan | 4 to | 12 wks | 2 - 3 wks | 0.5 - 2 wks | 2 wks | 1 - 2 wks | 2 wks | Plan | 1 - 2 wks | 1 - 2 wks |  | 1 wk |  | 1 - 3 wks | Plan
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
1 | EXTERNAL AUDIT SERVICES |  |  | 17500 | Post Review | Plan | N/A | NA | NA | NA | N/A | N/A | Plan | N/A | NA | NA | NA | N/A | N/A | N/A | Plan | NA | NA | NA | 1-20wks | N/A | 1-20wks | Plan | NA | NA | 1-26weeks | N/A
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
2 | CURRICULUM DEVELOPMENT LOCAL, NATIONAL ACCREDITATION AND INTERNATIONAL |  |  | 75000 | Post Review | Plan | N/A | NA | NA | NA | N/A | N/A | Plan | N/A | NA | NA | NA | N/A | N/A | N/A | Plan | NA | NA | NA | 1-20wks | N/A | 1-20wks | Plan | NA | NA | 1-26weeks | N/A
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
3 | e-PUBLICATIONS(WEB 0F SCIENCE) |  |  | 85000 | Post Review | Plan | N/A | NA | NA | NA | N/A | N/A | Plan | N/A | NA | NA | NA | N/A | N/A | N/A | Plan | NA | NA | NA | 1-20wks | N/A | 1-20wks | Plan | NA | NA | 1-26weeks | N/A
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
4 | ENVIRONMENTAL IMPACT CONSULTANT |  |  | 15000 | Post Review | Plan | N/A | NA | NA | NA | N/A | N/A | Plan | N/A | NA | NA | NA | N/A | N/A | N/A | Plan | NA | NA | NA | 1-20wks | N/A | 1-20wks | Plan | NA | NA | 1-26weeks | N/A
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
| TOTAL AMOUNT |  |  | 192500 |  | Plan | [6 empty] | Plan | [7 empty] | Plan |  |  | #VALUE! |  |  |  | Plan |  |  |  | #VALUE!
[6 empty] | Actual | [6 empty] | Actual | [7 empty] | Actual | [6 empty] | Actual
Note on B5: user:

## Procurement Plan Training
NATIONAL UNIVERSITIES COMMISSION
AFRICA CENTRES OF EXCELLENCE PROJECT (ACE)
CENTRE OF EXCELLENCE IN AGRICULTURAL DEVELOPMENT AND SUSTAINABLE ENVIRONMENT
CREDIT NO: ACE 023
TRAINING/CAPACITY BUILDING
S/N | DESCRIPTION | NAMES OF PARTICIPANTS | OBJECTIVES | OUTCOME | TRAINING LOCATION | COST
1 | MANAGEMENT TRAINING | 1.DIRECTOR 2.DEPUTY DIRECTOR 3.MONITORING & EVALUATION OFFICER 4.CENTRE ACCOUNTANT 5.PROCUREMENT OFFICER 6.INTERNAL AUDITOR | TRAINING IN PROJECT MANAGEMENT FOR WORLD BANK PROJECTS AND OTHER GRANTS | SPECIALISING IN THE DIFFERENT AREAS OF PROJECT MANAGEMENT | EU\USA | 300000
2 | TECHNICAL TRAINING 1.LABORATORY INSTRUMENTATION | LABORATORY TECHNOLOGISTS (3) | TRAINING ON STATISTICS, TROUBLE SHOOTING, AND USE OF LABORATORY EQUIPMENT | MAINTENANCE AND OPTIMUM USE OF ACQUIRED LABORATORY EQUIPMENT | INSTRUMENT MANIFACTURING LOCATIONS, (UK, USA/SA) | 170000
| 2. EXPERIMENTAL TECHNIQUES | ACADEMIC STAFF (3) | LEARN NEW TECHNIQUES IN COLLABORATING PARTNER'S LABORATORIES | COMPETENCE IN RESEARCH WORK TO ACCEPTABLE STANDARD FOR PUBLICATIONS
3 | TRAINING OF FINANCIAL OFFICER IN WORLD BANK GUIDELINES AND FIDUCIARY METHODS | ACCOUNTANTS, AUDITOR AND THE DIRECTOR | MANAGEMENT OF ACCOUNTING PROCEDURE | VERSATILITY IN ANALYSIS AND REPORTING | NIGERIA | 20000
4 | STUDENT CONFERENCES/TRAINING /WORKSHOPS SEMINARS | 40% OF TOTAL NO OF STUDENTS FOR CONFERENCES, WORKSHOP FOR SKILL AQUISITION | TO TRAIN STUDENTS, ATTENDANCE AT CONFERENCES, WORKSHOPS FOR SPECIAL SKILLS | ATTAINMENT OF COMPETENCE & NETWORKING | NIGERIA | 40000
5 | COST PROCUREMENT TRAINING | 1. PROCUREMENT OFFICER 2. DIRECTOR | WORLD BANK AND NATIONAL PROCUREMENT PROCUREMENT PROCEDURES | VERSATILITY IN PROCUREMENT PROCEDURES | NIGERIA & OVERSEAS | 38750
6 | SAFEGUARD TRAINING | 1. DIRECTOR 2. SAFEGUARD OFFICER | TRAIN FOR REPORTING FOR COMPLIANCE WITH ENVIRONMENTL IMPACT | REGULAR REPORTS ON COMPLIANCE WITH SAFEGUARD | USA | 33700
7 | ADMIN TRAINING | 1. ADMIN OFFICER (2) 2. ICT OFFICER 3. BUDGET OFFICER | TRAINING IN ADMIN SKILLS | VERSATILITY IN ADMIN PROCEDURES | NIGERIA | 20000
[5 empty] | TOTAL | 622450

## Disbursement Plan
NATIONAL UNIVERSITIES COMMISSION
AFRICA CENTRES OF EXCELLENCE PROJECT (ACE)
CENTRE OF EXCELLENCE IN AGRICULTURAL DEVELOPMENT AND SUSTAINABLE ENVIRONMENT
CREDIT NO: ACE 023
DISBURSEMENT PLAN (JANUARY - DECEMBER, 2017)
S/N | ACTIVITIES | OBJECTIVE | AMOUNT | MONTHS
|  |  | $ | JAN | FEB | MAR | APR | MAY | JUN | JUL | AUG | SEP | OCT | NOV | DEC | TOTAL
GOODS
1 | LOT 1 RESEARCH/FARM/ LABORATORY EQUIPMENT | STUDENT'S RESEARCH WORK | AMOUNT $: 75000; MONTHS TOTAL: 75000
2 | LOT 2 RESEARCH/FARM/LABORATORY EQUIPMENT |  | AMOUNT $: 55000; MONTHS TOTAL: 55000
3 | LOT 3 RESEARCH/FARM/LABORATORY EQUIPMENT |  | AMOUNT $: 90000; MONTHS TOTAL: 90000
4 | LOT 1 EXPERIMENTAL CONSUMABLES |  | AMOUNT $: 150000; MONTHS TOTAL: 150000
5 | LOT 2 RESEARCH CONSUMABLES |  | AMOUNT $: 30000; MONTHS TOTAL: 30000
6 | LOT 1 TEACHING AND MULTIMEDIA EQUIPMENT | TEACHING AIDS & E-LIBRARY | AMOUNT $: 340000; MONTHS TOTAL: 340000
7 | LOT 2 TEACHING AND MULTIMEDIA EQUIPMENT |  | AMOUNT $: 80000; MONTHS TOTAL: 80000
|  |  | 820000 | [12 empty] | 820000
TRAINING
1 | MANAGEMENT TRAINING | TRAINING IN PROJECT MANAGEMENT FOR WORLD BANK PROJECTS AND OTHER GRANTS | AMOUNT $: 300000; MONTHS TOTAL: 300000
2 | TECHNICAL TRAINING 1.LABORATORY INSTRUMENTATION | TRAINING ON STATISTICS, TROUBLE SHOOTING, AND USE OF LABORATORY EQUIPMENT | AMOUNT $: 170000; MONTHS TOTAL: 170000
| 2. EXPERIMENTAL TECHNIQUES | LEARN NEW TECHNIQUES IN COLLABORATING PARTNER'S LABORATORIES | bar: MONTHS MAY to MONTHS JUL
3 | TRAINING OF FINANCIAL OFFICER IN WORLD BANK GUIDELINES AND FIDUCIARY METHODS | MANAGEMENT OF ACCOUNTING PROCEDURE | AMOUNT $: 20000; MONTHS TOTAL: 20000
4 | STUDENT CONFERENCES/TRAINING /WORKSHOPS SEMINARS | TO TRAIN STUDENTS, ATTENDANCE AT CONFERENCES, WORKSHOPS FOR SPECIAL SKILLS | AMOUNT $: 40000; MONTHS TOTAL: 40000
5 | COST PROCUREMENT TRAINING | WORLD BANK AND NATIONAL PROCUREMENT PROCUREMENT PROCEDURES | AMOUNT $: 38750; MONTHS TOTAL: 38750
6 | SAFEGUARD TRAINING | TRAIN FOR REPORTING FOR COMPLIANCE WITH ENVIRONMENTL IMPACT | AMOUNT $: 33700; MONTHS TOTAL: 33700
7 | ADMIN TRAINING | TRAINING IN ADMIN SKILLS AND PROFICIENCY | AMOUNT $: 20000; MONTHS TOTAL: 20000
| TOTAL |  | AMOUNT $: 622450; MONTHS TOTAL: 622450
CONSULTANCIES
1 | EXTERNAL AUDIT SERVICES |  | AMOUNT $: 17500; MONTHS TOTAL: 17500
2 | CURRICULUM DEVELOPMENT LOCAL, NATIONAL ACCREDITATION AND INTERNATIONAL |  | AMOUNT $: 75000; MONTHS TOTAL: 75000
3 | e-PUBLICATIONS(WEB 0F SCIENCE) |  | AMOUNT $: 85000; MONTHS TOTAL: 85000
4 | ENVIRONMENTAL IMPACT CONSULTANT |  | AMOUNT $: 15000; MONTHS TOTAL: 15000
| TOTAL |  | AMOUNT $: 192500; MONTHS TOTAL: 192500
|  |  | MONTHS TOTAL: 0 | 112229.1667
OPERATING COST
1 | Running cost for the whole year activities. | to achieve efficiency and effectiveness in the activities of the Centre | AMOUNT $: 1346750; MONTHS TOTAL: 1346750 |  | 0
2 |  |  | AMOUNT $: MINOR WORKS
| Hostel Refurbishment | Refurbishment of Post Graduate Hostel for Regional Students | AMOUNT $: 200000; MONTHS TOTAL: 200000
| Furnishing of Postgraduate Hostels | Refurbishment of Post Graduate Hostel for Regional Students | AMOUNT $: 80000; MONTHS TOTAL: 80000
| Upgrade of Goat and Sheep House | For Students Research Works and Training | AMOUNT $: 60000; MONTHS TOTAL: 60000
| Upgrade of Goat (Kalahari) House | For Students Research Works and Training | AMOUNT $: 50000; MONTHS TOTAL: 50000
| Upgrade of Growers Poultry House | For Students Research Works and Training | AMOUNT $: 60000; MONTHS TOTAL: 60000
| Upgrade of Layers Poultry House | For Students Research Works and Training | AMOUNT $: 60000; MONTHS TOTAL: 60000
| Upgrade of Cockerel Poultry House | For Students Research Works and Training | AMOUNT $: 50000; MONTHS TOTAL: 50000
| Upgrade of Laboratory (Plant Breeding/Seed Storage Laboratory) | For Students Research Works and Training | AMOUNT $: 70000; MONTHS TOTAL: 70000
| Replacement of Existing Screen House | For Students Research Works and Training | AMOUNT $: 50000; MONTHS TOTAL: 50000
| TOTAL |  | AMOUNT $: 680000; MONTHS TOTAL: 680000
|  |  | 3661700 | [12 empty] | 3661700

## MINOR WORKS
COUNTRY: NIGERIA
PROJECT: (AFRICA HIGHER EDUCATION CENTRES OF EXCELLENCE PROJECT) P126974
Loan No: 023
NAME OF INSTITUTION: FEDERAL UNIVERSITY OF AGRICULTURE, ABEOKUTA
GOODS | [8 empty] | Draft Bid Documents, including specs and quantities, draft SPN |  | If Post-Review, No-objection Dates are not needed
|  |  | BASIC DATA | [7 empty] | Spec Proc Notice Advert | Bidding Period |  | Bid Evaluation |  |  | Contract Finalization |  |  |  |  | Contract Implementation
S/NO. | Description OF CONTRACTS | Package Number | Lot Number | Estimated Amount in US $ | Procurement Method | Pre-or Post Qualification | Prior or Post Review | Plan vs. Actual | Prep & Submission by Ex Agency | No-objection Date | On-line UNDB Gateway Nat Press | Bid Invitation Date | Bid Closing-Opening | Submission Bid Eval Rpt | No-objection Date | Plan vs. Actual | Contract Amount in US$ | Date Contract Award | Date Contract Advert | Date Contract Signature | Opening of Let of Credit | Arrival of Goods | Inspection Final Acceptance
[6 empty] | If Prequalification |  | Plan | 4 - 7 wks | 1 - 1.5 wks | 1.5 - 2 wks | 6 to | 12 wks | 1.5 - 3 wks | 1 - 1.5 wks | Plan |  | 1 wk |  | 1.5-3 wks
[6 empty] | add 7-13 wks |  | Actual | [7 empty] | Actual
1 | Hostel Refurbishment |  |  | 200000 |  | Postqualification | Post review | Plan | N/A | N/A | N/A | 27/02/17 | 10/04/17 | 08/05/17 | N/A | Plan | 200000 | 05/06/17 |  | 28/06/17 | N/A | 05/07/17 | 04/09/17
[8 empty] | Actual | N/A | N/A | N/A |  |  |  |  | Actual
2 | Furnishing of Postgraduate Hostels |  |  | 80000 |  | Postqualification | Post review | Plan | N/A | N/A | N/A | 27/02/17 | 10/04/17 | 08/05/17 | N/A | Plan | 80000 | 05/06/17 |  | 28/06/17 | N/A | 05/07/17 | 04/09/17
[8 empty] | Actual | N/A | N/A | N/A |  |  |  |  | Actual
3 | Upgrade of Goat and Sheep House |  |  | 60000 |  | Postqualification | Post review | Plan | N/A | N/A | N/A | 27/02/17 | 10/04/17 | 08/05/17 | N/A | Plan | 60000 | 05/06/17 |  | 28/06/17 | N/A | 05/07/17 | 04/09/17
[8 empty] | Actual | N/A | N/A | N/A |  |  |  |  | Actual
4 | Upgrade of Goat (Kalahari) House |  |  | 50000 |  | Postqualification | Post review | Plan | N/A | N/A | N/A | 27/02/17 | 10/04/17 | 08/05/17 | N/A | Plan | 50000 | 05/06/17 |  | 28/06/17 | N/A | 05/07/17 | 04/09/17
[8 empty] | Actual | N/A | N/A | N/A |  |  |  |  | Actual
5 | Upgrade of Growers Poultry House |  |  | 60000 |  | Postqualification | Post review | Plan | N/A | N/A | N/A | 27/02/17 | 10/04/17 | 08/05/17 | N/A | Plan | 60000 | 05/06/17 |  | 28/06/17 | N/A | 05/07/17 | 04/09/17
[8 empty] | Actual | N/A | N/A | N/A |  |  |  |  | Actual
6 | Upgrade of Layers Poultry House |  |  | 60000 |  | Postqualification | Post review | Plan | N/A | N/A | N/A | 27/02/17 | 10/04/17 | 08/05/17 | N/A | Plan | 60000 | 05/06/17 |  | 28/06/17 | N/A | 05/07/17 | 04/09/17
[8 empty] | Actual | N/A | N/A | N/A |  |  |  |  | Actual
7 | Upgrade of Cockerel Poultry House |  |  | 50000 |  | Postqualification | Post review | Plan | N/A | N/A | N/A | 27/02/17 | 10/04/17 | 08/05/17 | N/A | Plan | 50000 | 05/06/17 |  | 28/06/17 | N/A | 05/07/17 | 04/09/17
[8 empty] | Actual | N/A | N/A | N/A |  |  |  |  | Actual
8 | Upgrade of Laboratory (Plant Breeding/Seed Storage Laboratory) |  |  | 70000 |  | Postqualification | Post review | Plan | N/A | N/A | N/A | 27/02/17 | 10/04/17 | 08/05/17 | N/A | Plan | 70000 | 05/06/17 |  | 28/06/17 | N/A | 05/07/17 | 04/09/17
[8 empty] | Actual | N/A | N/A | N/A |  |  |  |  | Actual
9 | Replacement of Existing Screen House |  |  | 50000 |  | Postqualification | Post review | Plan | N/A | N/A | N/A | 27/02/17 | 10/04/17 | 08/05/17 | N/A | Plan | 50000 | 05/06/17 |  | 28/06/17 | N/A | 05/07/17 | 04/09/17
[8 empty] | Actual | N/A | N/A | N/A |  |  |  |  | Actual
|  |  |  | 680000 | [12 empty] | 680000