## WORK PLAN
AFRICA CENTRES OF EXCELLENCE (ACE)
CENTRE OF EXCELLENCE IN AGRICULTURAL DEVELOPMENT AND SUSTAINABLE ENVIRONMENT, ABEOKUTA: WORK PLAN (JANUARY 2019 - MARCH 2020)
| CMP XX | [8 empty] | Year 2019/2020
Activity No | COMPONENT | ACTIVITIES | OBJECTIVE | JUSTIFICATION | OUTPUT | ESTIMATED BUDGET ($) |  |  | RESPONSIBLE UNIT | January 2019 - MARCH 2020
[6 empty] | Main | Partners | Total |  | January | Febrary | March | April | May | June | July | August | September | October | November | December | January | Febrary | March
Component 1: Strengthening Africa Centers of Excellence
DLR 1.1 | Running of CEADESE Office | Day-day running CEADESE Office | To acquire and install small office equipment, toners, cartridge, sevicing of equipment, etc | Requirement for the office to function | Efficiency | 7500 | 0 | 7500 | Director
|  | Procurement of Stationery and consumables | To acquire printing papers, pens, pencils, files, letterheads, etc. | Required for printing documents, for meetings, keeping records, etc. | Records | 1750 | 250 | 2000 | Director
|  | Procurement and Maintenance of Project Vehicle | 1) For fueling, servicing amd general maintenance of CEADESE vehicles. | For students trips, for errands, farms works, official travels, reception of consultants and travels, etc. | Efficiency | 6000 |  | 6000 | CEADESE Admin Officer
|  | Operational cost [Other operating costs, furging partnership, Developing implementation & Procurement Plan etc | Operational Expenses | Operational Expenses | Operational Expenses | 4000 | 0 | 4000 | Director
|  |  | Required for the several meetings to formulate the 2018 plans. | payment of meeting expenses | Production of 2017 Implementation, Work and Procurement Plans
|  |  | Required for furging partnerships | Expenses on travels, and production of MOUs | MOUs signed
|  | Cost of Advert/Contract | Required for placement of advertisements and communications | CEADESE information, telephone bills, internet data. | number of contacts, and advertisements | 1500 |  | 1500 | Director
DLR 1.2 | Coordination of Meetings | Coordinating CEADESE Meetings | Required to prepare for the various Centre meetings | Expenses for refreshments, payment of mileage for invited participants | Meeting records | 3000 |  | 3000 | CEADESE Admin Officer
7 | Attendance at World Bank/ AAU Workshops | Attending World Bank meetings and Workshops | Required for attending World Bank and AAU organised workshops. | Expenses for travels, estacodes, DTA. | Progress reports of achivements presented at workshops. | 70550 | 17450 | 88000 | Director
DLR 1.4 | Technical & Management Trainings | Trainings (Management Faculty and Technologists) | Required to train the management team of the Centre in Project management nationally and internationally, train faculty to enhance teaching and research skills, and to enhance the analytical skills of technologist. | Expenses for course fee, travels, estacodes, DTA for Centre Leader, deputy, M&E, Accountant, Audit, Procurement, some faculty. 1) Members of CEADESE Management Team; 2) CEADESE Programme Leaders; 3) Relevant Deans | Number of officers to be trained (Centre Officers, University Management Officers, Technologists, College Deans, Programme Leaders). Some faculty Certificates of attendance. | 86750 | 13250 | 100000 | Director
DLR 1.5 | Travels (Local & International) | Travels (Local & International) | Travels by officers and faculty on official assignments | Expenses incurred on travels, mileage, Estacodes, DTA. | Meeting records and reports | 35000 | 5000 | 40000 | Accountant
DLR 1.6 | Running of CEADESE website | Running of CEADESE website | 1) Web hosting and updating | Expenses on web hosting by ICT Unit of University | For transparancy | 800 | 0 | 800 | Information Officer
|  |  | 2)Subscription to internet and online journals | Expenses on web hosting by ICT Unit of University | For transparancy | 57820.09 | 0 | 57820.09
DLR 1.10 | Facilitation of CEADESE Communication office | Facilitation of CEADESE Communication office | Required by the Communications officer Projecting image and activities of the Centre | Expenses on communication needs, photography, liaison with press and AAU | Reporting Centre activities in press and bulletins | 4000 |  | 4000 | Communications Officer
DLR 2.1 | Runing Short-term courses for Students | Teaching Materials and softwares | Required for procurement of teaching | Expenses on procuring course materials for short term courses | Short terms courses delivered and number of participants. | 23000 |  | 23000 | Deputy Director
|  | Admission advertisements | Required for advertising for participants in short term courses. | Cost of advertisement placement in newspapers. | Hard copies of advertisements and number of respondents. | 1500 | 500 | 2000 | Director
|  | Operational Cost for Short term courses | Required for impacting practical knowledge. | For additional practical knowledge to for students and stakeholders in agriculture. | Number of short term courses held and participants. | 16312.67 | 7000 | 23312.67 | Accountant
|  | Publication of short term courses reports. | Required for the dissemination of short term courses activities | References materials for students and stakeholders | Hard copies of publications | 4000 | 1000 | 5000
|  | Airfare & Accommodation for Resource Persons | Required for the passage & comfort of resource persons | Cost of aur ticket, hotel accomodation of resource persons | skill & knowledge enhancement | 35000 |  | 35000
|  | Honorarium for resource persons | Required as service charge for resource persons | Cost of fees charged by the facilitators of short term courses | skill & knowledge enhancement | 35000 |  | 35000
DLR 2.2 | Running Masters Students Degree Courses | Running language course | For teaching English and French languages | This is to enhance the english of francophone students and to attract regional students from non english speaking countries. | Number of students taught. | 5000 |  | 5000 | M & E Officer
|  | Revision of curricula | Required for yearly updating of teaching curricula |  | Revised curricula, number of courses revised. | 5000 |  | 5000
|  | Operational Cost | For students travels, field trips, attendance of conferences and short term courses. | To enhance knowledge, networking, presentation of research works at conferences. | Number of students that benefitted, presentations and payment records. | 12000 | 3000 | 15000
|  | Cost of adverts | Placement of Advertisements for admission | For the recruitment of quality candidates | Number of subscriptions and admited candidates, newspaper publications | 5000 |  | 5000
|  | Scholarship awards [Cost for 5 Msc regional students & 12 Nigerians IRO Tuition, books Etc.] | To award various grades of scholarships for outstanding candidates | To attract good students and to attract regional students from poor countries. | Number of awards and cost. | 10000 |  | 10000
|  | Cost of research Consumables and accessories | purchase of consumables tor the laboratory for student use | To enhance qualitative researcjh | Problem solving research output/result | 92818.46 | 25704.61 | 118523.07
DLR 2.3 | Running PhD Degree Courses | Running language courses | For teaching English and French languages | This is to enhance the english of francophone students and to attract regional students from non english speaking countries. | Number of students taught. | 5000 |  | 5000 | M & E Officer
|  | Revision of curricula | Required for yearly updating of teaching curricula |  | Revised curricula, number of courses revised. | 5000 |  | 5000
|  | Operational Cost | For students travels, field trips, attendance of conferences and short term courses. | To enhance knowledge, networking, presentation of research works at conferences. | Number of students that benefitted, presentations and payment records. | 12000 | 3000 | 15000
|  | Cost of adverts | Placement of Advertisements for admission | For the recruitment of quality candidates | Number of subscriptions and admited candidates, newspaper publications | 5000 |  | 5000
|  | Cost of research Consumables and accessories | purchase of consumables tor the laboratory for student use | To enhance qualitative researcjh | Problem solving research output/result | 127896.87 | 75724.22 | 203621.09
|  | Scholarship awards [Cost for 3 PhD regional studentS IRO Tuition,upkeep,books,accommodation etc.] | To award various grades of scholarships for outstanding candidates | To attract good students and to attract regional students from poor countries. | Number of awards and cost. | 20000 |  | 20000
DLR 2.4 | Outreach “periods” (faculty and students) | Travel and Maintenance expenses by M.AgSE Students | Required to meet students expenses during internships or certified training in other laboratories. | For transports fares, living expenses | Record of internship placements and payment vouchers. | 10000 | 0 | 10000 | Deputy Director
|  | Travel and Maintenance expenses for PhD.AgSE Students | Required to meet students expenses during internships or certified training in other laboratories. | For transports fares, living expenses | Record of internship placements and payment vouchers. | 10000 | 0 | 10000
|  | Operational Cost | Required for faculty expenses for internship supervision, Training of faculty in other institutions or laboratories. | Faculty need to visit interns at their placement industries/collaborating institutions. | Number of faculty involved and evidence of training evidence, Short term courses certificates. | 5000 | 0 | 5000
|  |  | For community Service, collaborative research and skill acquisition | Needed for service to industry and knowledge dissemination and acquisition | Number of faculty on outreach in other establishments.
| Gap assessment certified/self evaluation | Procurement of Stationery | Production of documents required for assessment and remuneration of assessors |  |  | 9000 | 1000 | 10000
| International Accreditation | International Accreditation | To complete international accreditation of all the Centre's programmes | Payment of Accreditation fee balance. Activity required for international recognision of the Centre programmes. | Certificate of accreditation | 178942.33 |  | 178942.33
|  | Meetings | To hold series of meetings to address issues raised by international accreditors | Funding of meetings by provisions of food, drinks and other logistics | Certificate of accreditation | 34000 | 6000 | 40000
|  | Printing and Publication | To Print and publish of accreditation reports. | Cost of printing and publication | Certificate of accreditation | 42500 | 7500 | 50000
|  | Publicity | To publicise CEADESE programmes after being internationally accredited | Cost of media publicity and other viable forms of publicity | Better awareness and attraction of more students | 21250 | 3750 | 25000
DLR 2.6 | Number of papers published in Internationally recognized and Peer-Review Journal | Research and Research support | To conduct standand research that would be published in recognised journals and adoptable findings. | Expenses for executing standard research work to generate publications and publication charges. | Number of students thesis, publications and adoptable research findings | 39031.85 | 10000 | 49031.85 | M & E Officer
|  | Research theses/dissertations preparation for postgraduate School approval for 45 students | Required for assisting final thesis binding | Expenses on thesis preparation | Number of theses completed | 10000 |  | 10000
|  | 1) Publication 2) Site for research repository | 1) Required for publishing research findings in journals 2) Repository for research findings | 1) Expenses on page charges 2) Deposit of research findings | Number of papers published in high impact journals | 10000 |  | 10000
|  | lresearch equipment | To procure light research equipment | cost of light research equipment to generate revenue for the centre | Improved research output | 330000 | 125326.43 | 455326.43
DLR 2.7 | Externally generated Revenue | Activities for generating External Revenue | Fund raising through short term coursess, right shops to specifically respond to grant calls, trainings,equipments , revenue generation through our laboratories and farms., and consultancy services | Cost associated with worshops, grant seeking, training and purchase of laboratory and farm consumables | Record of amount generated | 174514.97 | 0 | 174514.97 | Finance Officer
DLR 2.8 | Meeting milestones for improved learning and research environment specified in the Performance and Funding Contracts | Milestone 2 | Procurement | Refurbishment of Students Hostel and Computer Laboratory for conducive accommodation and learning environment | Amenities provided/Evidence of Structure refurbished and verified by Procurement consultants | 0 | 0 | 0
|  | Milestone 3 | For the procurement of research equipment and consumables for the conduct of standard and publishable research works. | For conducting standard publishable research works by students and faculty | All equipment and consumables listed on approved procurement plan | 40000 | 0 | 40000
|  | Milestone 4 | Procurement | This is to improve research buildings such as animal houses and plant production facilities to international standards including students hostels, classrooms and laboratories. | Upgrade 7 research research facilities (buildings housing animals and equipment) | 16832.17 | 0 | 16832.17
DLR 3.1 | Timely withdrawal application supported by financial reporting for the ACE account for the period | Running upgraded accounting system | Updating and upgrading of accounting packages. Servicing | This is required to keep our system up to date and engage the provider. This is to enhance timely submission of accounting reports | Record of submitted reports. | 1800 |  | 1800 | Finanvce Officer
|  | Training of financial Officer in World Bank guidelines and fiduciary methods | Centre officials to go on regular training to update skill on fiduciary methods as organised bu AAU/WB/NUC or by independent trainers. | For updating skill | Number of trainings and evidence of attendance. | 5000 |  | 5000
|  | Cost of Training | Payment for training fees, accommodation and transportation for financial officers in respect of relevant professional acccounting trainings and software training | For professional shills & training update | Efficiency | 24703.75 |  | 24703.75
DLR 3.2 | Functioning University audit Committee under the university council | Meetings (audit committees) | Audit committee meeting on quarterly basis for consideration of internal audit reports and annual external audit report. | Required for fund disbursement | Reports | 2000 |  | 2000 | Chairman of Audit Committee
|  | Operational Cost | Cost for holding meetings |  | Vouchers and minutes | 2000 |  | 2000
DLR 3.3 | Functioning internal audit unit for the university | Internal auditing | Auditing of all payments and procurements is mandatory. Quarterly reports for presentation to WB | Mandatory | Reports submitted and on website | 3500 |  | 3500 | Internal Audit Officer
|  | External auditing accounts | Annual external audit to be conducted | Mandatory | Report submitted and displayed on website | 1500 |  | 1500
DLR 3.4 | Web Transparency on Financial management (web-access to audit reports,interim financial reports, budgets and annual work plan) | Display of all Reports on website | To demonstrate financial transparency, all reports and finantial audit to be displayed on Centre website | Mandatory | Disclosures on website | 25000 |  | 25000 | Information Officer
DLR 4.1 | [7 empty] | 0
DLR 4.2 | Timeliness of procurement progress | Bids advertisement | Advertisements in national newspapers and on website |  |  | 5000 |  | 5000 | Procurement Officer
|  | Operational Cost | Procurement office management |  | records | 2000 |  | 2000
|  | Training | Training of procurement officer and staff |  | Certificate of training | 25140 |  | 25140
|  | Cost of bid evaluation | Cost associated with bid opening | Payment to observers, refreshments etc | records | 2000 |  | 2000
|  | Cost of producing bid document | Printing of bid documents | Printing of bid documents | records | 2000 |  | 2000
Implementation Committee
|  | Total |  |  |  | 1730913.16 | 305455.26 | 2036368.42

## BUDGET
World Bank-Africa Centre of Excellence: CEADESE-FUNAAB
BUDGET LINE ANALYSIS-2019/2020
Code | Relevant DLI | Activity | Budget Estimate (USD)
|  |  | ACE leader | Partners | Total
|  |  | (Component total for ACE leader) | (Component total for partners) | (Total of component)
DLI 1 |  | Institutional Readiness
DLR 1.1 |  | Running of CEADESE Office
|  | Cost of running CEADESE Office | 7500 |  | 7500
|  | Cost of stationery and consumables | 1750 | 250 | 2000
|  | Cost of running Project Vehicles | 6000 |  | 6000
|  | Cost of adverts / contacts | 1500 |  | 1500
|  | Operational cost | 4000 |  | 4000
|  | TOTAL | 20750 | 250 | 21000
DLR 1.2 |  | Coordination of Meetings
|  | Cost of Coordinating CEADESE Meetings | 3000 |  | 3000
|  | TOTAL | 3000 |  | 3000
DLR 1.3 |  | Attendance at World Bank/ AAU Meetings
|  | Cost of attending World Bank meetings and Workshops | 70550 | 17450 | 88000
|  | TOTAL | 70550 | 17450 | 88000
DLR 1.4 |  | Technical & Management Trainings
|  | Cost of training (Management and Faculty) | 86750 | 13250 | 100000
|  | TOTAL | 86750 | 13250 | 100000
DLR 1.5 |  | Travels (Local & International) | 35000 | 5000 | 40000
DLR 1.6 |  | Running of CEADESE website
|  | Web hosting and updating | 800 |  | 800
|  | Subscription to internet and online journals | 57820.09 |  | 57820.09
|  | TOTAL | 58620.09 |  | 58620.09
DLR 1.10 |  | Facilitation of FUNAAB Communication office | 4000 | 0 | 4000
|  |  | 4000 |  | 4000
|  | TOTAL FOR DLR 1 | 278670.09 | 35950 | 314620.09
DLR 2.0 |  | Teaching and Learning Resources
DLR 2.1 |  | Short-term courses
|  | Teaching Materials and softwares | 23000 |  | 23000
|  | Admission advertisements | 1500 | 500 | 2000
|  | Airfare & Accommodation for Resource Persons | 35000 |  | 35000
|  | Honorarium for resource persons | 35000 |  | 35000
|  | Operational Cost for short term courses | 16312.67 | 7000 | 23312.67
|  | Publication of short term courses reports | 4000 | 1000 | 5000
|  | TOTAL | 114812.67 | 8500 | 123312.67
DLR 2.2 |  | Masters Students
|  | Cost of running language course | 5000 |  | 5000
|  | Cost of revising curricula | 5000 |  | 5000
|  | Operational Cost | 12000 | 3000 | 15000
|  | Cost of research Consumables, light equipment and accessories | 92818.46 | 25704.61 | 118523.07
|  | Cost of adverts | 5000 |  | 5000
|  | Cost of Scholarship awards | 10000 |  | 10000
|  | TOTAL | 129818.46 | 28704.61 | 158523.07
DLR 2.3 |  | PhD Students
|  | Cost of running language course | 5000 |  | 5000
|  | Cost of revising curricula | 5000 |  | 5000
|  | Operational Cost | 12000 | 3000 | 15000
|  | Cost of research Consumables, light equipment and accessories | 127896.87 | 75724.22 | 203621.09
|  | Cost of adverts | 5000 |  | 5000
|  | Cost of Scholarship awards | 20000 |  | 20000
|  | TOTAL | 174896.87 | 78724.22 | 253621.09
DLR 2.4 |  | Outreach “periods” (faculty and students)
|  | Travel and Maintenance expenses by M.AgSE Students | 10000 |  | 10000
|  | Travel and Maintenance expenses by PhD.AgSE Students | 10000 |  | 10000
|  | Operational Cost | 5000 |  | 5000
|  | TOTAL | 25000 |  | 25000
DLR 2.5 |  | Accreditation
Gap assessment certified/self evaluation
|  | Cost of stationery | 9000 | 1000 | 10000
|  | Meetings | 34000 | 6000 | 40000
|  | Printing and Publication | 42500 | 7500 | 50000
|  | Publicity | 21250 | 3750 | 25000
|  | International Accreditation | 178942.33 |  | 178942.33
|  | TOTAL | 285692.33 | 18250 | 303942.33
DLR 2.6 |  | Number of papers published in Internationally recognized and Peer-Review Journal
|  | Cost of research support | 39031.85 | 10000 | 49031.85
|  | Light research equipment | 330000 | 125326.43 | 455326.43
|  | Costs of research theses/dissertations for 30 students | 10000 |  | 10000
|  | Costs of publications (page charges) | 10000 |  | 10000
|  | TOTAL | 389031.85 | 135326.43 | 524358.28
DLR 2.7 |  | Externally generated Revenue | 174514.97 |  | 174514.97
DLR 2.8 |  | Meeting milestones for improved learning and research environment specified in the Performance and Funding Contracts |  |  |  | 0
|  | cost of civil works | 16832.17 |  | 16832.17
|  | cost of equipment and lab purchases | 40000 |  | 40000
|  | Establishment of research core facilities | 0 |  | 0
|  | TOTAL | 56832.17 |  | 56832.17
|  | TOTAL FOR DLI 2 | 1350599.32 | 269505.26 | 1620104.58
DLR 3.0 |  | Financial Management
DLR 3.1 |  | Timely withdrawal application supported by financial reporting for the ACE account for the period
|  | Cost of running upgraded accounting system | 1800 |  | 1800
|  | Training of financial Officer in World Bank guidelines and fiduciary methods | 5000 |  | 5000
|  | Cost of Training | 24703.75 |  | 24703.75
|  | TOTAL | 31503.75 |  | 31503.75
DLR 3.2 |  | Functioning University audit Committee under the university council
|  | Operational Cost | 2000 |  | 2000
|  | Cost of Audit Committee Meetings | 2000 |  | 2000
|  | TOTAL | 4000 |  | 4000
DLR 3.3 |  | Functioning internal audit unit for the university
|  | Cost of hiring external auditor | 3500 |  | 3500
|  | Cost of auditing accounts | 1500 |  | 1500
|  | TOTAL | 5000 |  | 5000
DLR 3.4 |  | Web Transparency on Financial management (web-access to audit reports,interim financial reports, budgets and annual work plan) | 25000 |  | 25000
|  | TOTAL FOR DLI 3 | 65503.75 |  | 65503.75
DLR 4.0 |  | Procurement
DLR 4.1 |  | Third Party procurement process verification
DLR 4.2 |  | Timeliness of procurement progress
|  | Cost of bid advertisement | 5000 |  | 5000
|  | Operational Cost | 2000 |  | 2000
|  | Cost of Training | 25140 |  | 25140
|  | Cost of bid evaluation | 2000 |  | 2000
|  | Cost of producing bid document | 2000 |  | 2000
|  | TOTAL FOR DLI 4 | 36140 |  | 36140
|  | GRAND TOTAL | 1730913.16 | 305455.26 | 2036368.42
|  | % for partners |  |  | 0.15