General

1. The second revised submissions were carried out based on where the Centre has money, and what the Centre needs to spend money on, to be able to maintain momentum and sustainability. It was also based on the need to stretch the budget to March 2020 as advised.

2. The new budget lines titled "cost of research consumables, light equipment and accessories" were included in the Masters Students and PhD Students to service the new CEADESE Laboratory as a continuation of research supports which CEADESE usually gives to students.

3. Errors on titles and headings indication proper dates have been addressed

Specifics

4. On DLI 1.3, we have reduced the "accreditation" budget to have a budget increase on "Attendance at AAU/WB Meetings" from 38,000 USD to 88,000 USD.

5. On DLI 1.4, we have reduced the "accreditation" budget to have a budget increase of "Technical and Management Training" from 65,000 USD to 100,000 USD

6. On DLI 1.5, we have reduced the "No of Papers Published" budget to have a budget increase on "Travels, Local and International" from 20,000 USD to 40,000 USD.

7. On DLI 1.6, we have reduced the "No of Papers Published" and "accreditation" budget  to have a budget increase on "Internet Subscription" from 1,820.09 USD to 57,820.09 USD.

8. On DLI 1.10, we have reduced the "No of Papers Published" budget to have a budget increase on "Facilitation of FUNAAB Communication Office" from Zero USD to 4,000 USD.

9. On DLI 2.4, we have reduced the "PhD Students" budget to have a budget increase of "Outreach" from Zero USD to 25,000 USD

Comments to updated draft Annual Work Plan for 2019-2020 from CEADESE

While the updated workplan and budget respond to most of the questions it is so radical different that it raises quite a few new questions. These need to be clarified before the Annual Work Plan for 2019-2020 from CEADESE can be approved.

The updated workplan has a higher total budget that reflects that it according to the ‘Responses to Comments’ now covers the remaining project period until March 2020 (see CEADESE text in red below). However, the headings of the Work Plan and Budget documents remain indicating only 2019? As for the procurement document the first sheet labelled ‘Work Plan’ seems to cover 2017, while the remaining sheets are correctly labelled with two period (as indicated in responses).

We have readjusted the Workplan, Budget, and Procurement plan accordingly to cover January 2019 to March 2020. This has been reflected in the spreadsheets. The spreadsheets therefore have “January to September 2019” and “October 2019 to March 2020” accordingly.

General:

- The general concern is to what degree the current workplan will trigger sufficient funds to secure the planned investments, especially within DLI 2.8. In the requested narrative,please write-up estimate the funds you expect to trigger based on the proposed workplan to see if all your investments are justified.

We have adjusted the budget accordingly to meet our current financial reality

It is not evident from the updated workplan and the brief narrative (in red) how this significantly different workplan and budget has been designed to better target the need for triggering DLI’s and strengthening CEADESE sustainability? There seems to have been major reallocations without justification and they are therefore not easy understandable. The major ones are listed below:

DLR 1:

- DLR 1.1 Running cost of project vehicle - how can it go from USD 70,426 to USD 6,000? Was there planned purchase of cars in the first budget? No explanation on the consequences of reducing this budget with 90 %?

- DLR 1.1 Operational cost reduced from USD 20,000 to USD 4,000 again without indication of effect on quality of service?

- DLR 1.3Cost of attending World Bank workshops reduced from USD 161,750 to USD 38,000 - does that mean that the delegation from CEADESE will be reduced with ¾?

- DLR 1.4Cost of training Management and Faculty reduced from USD 270,000 to USD 65,000 - again what is the consequence of reducing the budget to ¼? What planned training will be omitted and with what consequences?

- DLR 1.6Subscription to internet and online journals goes from USD 108,800 to USD 1,820. Less than 2 % of the earlier budget, does that mean that CEADESE close its internet and journal subscription? At the same time in DLR 3.4 Web Transparency on    Financial management (web-access to audit reports,interim financial reports, budgets and annual work plan) has changed from USD 800 to USD 25,000. So you reduce the budget for internet access with 98 % and increase the budget for Web Transparency 31 times. Please explain?

DLR 2:

- DLR 2.1 While the budget says shortterm courses the work plan still talks about Workshops.

- In DLR 2.2 you add a new item ‘Cost of research Consumables and accessories’ at USD 118, 523 and for DLR 2.3 on USD 228,621 and at the same time you say under DLR 2.4 that you can’t afford USD 60,000 previously allocated for this activity. Please explain this significant change in priority?

- Also, you write in your comments that DLR 2.2 now slightly adjusted again. Changing from USD 40,000 to USD 158,523 would by most be considered more than a slight adjustment. Please explain?

- For DLR 2.5 Accreditation the budget has gone ballistic from USD 69,719 to USD 458,942. What happened here? It makes no sense if the cost of accreditation is the same as the DLR triggering effect. Please explain why the cost for this item has exploded?

- DLR 2.6 is also changed significantly from USD 178,000 to USD 554,358. Was this previous budgeted under 2.8? There is no justification for a significant budget increase within an area that don’t trigger more funds, while at the same time you say you can’t afford Internship - your flagship achievement (that don’t either trigger more funds). Please justify?

DLR 3

- In DLR 3.1 there is added a cost of training of USD 24,703. Were you not aware of this cost then you submitted the first workplan and budget?

- The budget for partnerships is critically low with only 3.7 % allocated for partners.Please modify partnership budget to meet the project requirement of 15 %.

The 15% allocation to partners has been adjusted

The partnership share of the budget is now at the expected level and thereby approved.

- The presented workplan/budget is very detailed, but it does not come across as being specifically designed to secure the two things that is most pertinent for CEADESE right now:

  - Ensuring that as many of the DLI’s remaining are triggered before the closure of ACE I

What about DLI 2.1? On DLI 2.5, the international accreditation exercise was conducted from November 19 to 30, and we are awaiting the official results, which we expect will trigger the DLI. But the cost seems to almost override the funds triggered? On 2.7, specific activities have been designed to trigger the funds. Please elaborate more on this as it has been a notorious weak point for CEADESE. On DLI 2.8, we have completed all outstanding projects, and we are awaiting NUC/WB verification.This had been communicated to the WB/AAU since October 2018. With this, the DLIs for 2.8 will be triggered. Noted.

  - Developing a sustainability plan that considers the fact that CEADESE is not being funded under ACE Impact

The plan includes Short term courses, Strategic recruitment campaign for foreign students,Funds for this seems to have been reduced in the update budget.  Meetings and Interactions with Governments and Companies for consultancy services, and use of CEADESE laboratory for specialised to generate some IGR. How much IGR is this expected to trigger?

- It is also a bit confusing that you operate with DLR 1.1 - DLR 1.10 when DLR 1 is about Effectiveness and was accomplished at project start. Please renumber them Activity 1 - 10 and use Activity 1.1 at each sub-activity for easy reference. Also, for the other DLI’s please give each sub-activity a discrete number.

This has been addressedCan not see this has been addressed

- There is no subtotal for each group of activities (DLR’s) please add those.

This has been addressedThis was actually done the previous Budget but with several errors (especially DLR 2.2)

Specific at sub-activity level

- DLI 1.1 sub activity 3 seems to have a slightly misguiding heading ‘Maintenance of Project Vehicles’. ‘Running cost for vehicles’ would be better and then have the objective and justification. This are quite new vehicles and they should not need that much maintenance.

This has been addressedWhat was the USD 64,000 previously allocated under this budgeted for? A new vehicle?

- DLI 1.1 sub activity 4 has diverse activities and three objectives?Budget allocation under this activity is not very clear either. It seems to be partly investment into forging new partnership (is that correct?), partly to develop the 2019 Implementation Plan (but is that not what you are already presenting here). Please clarify?

This DLI is neither for forging new partnerships nor developing 2019 IP. It is simply for communications.Table in Work Plan still misguiding here.

- DLR 1.3 WB/AAU Workshop attendance, the partnership part of the budget is low, what can you do with USD 1,750? Please justify.

This has beenaddressedYes partnership budget has been increased but own budget has been severely cut. No explanations of consequences?

- DLI 1.4 can this be part of DLI 2.2? Seems like short-term training.

- It is not short term training but training for Management of CEADESE. Infact the balance of the ToT training in Copenhagen has been factored into this.What is the impact of the severe budget cut? Will you e.g. chancel the contract with University of Copenhagen?

- DLI 1.5 CEADESE always seems to have a lavish travel budget in their workplan. Why is this not part of the different activities that requires travel? In almost all the activities above travel is part of the justification for the cost. How is this travel budget different from the travel cost under the different activities?

1.5  is specific for air ticket whereas budgets for all other activities that involves travels are also specific.

- DLI 2.1 Short-term courses, not sure why it says for students. Recommend either just ‘Short-term courses’ or ‘Short-term courses for sector stakeholders’.The bulk of the money under this DLI is for Workshop? Is this a mistake? Should it have been short-term courses? Please clarify. Is the funding for this activity adequate to accomplice 100 % on this DLR? Currently CEADESE has no verified achievements within this DLR.

‘for students’ clause removed. Also ‘workshop’ heading removed and replaced with ‘short term courses’Still called workshop in Work Plan.

- DLI 2.2 Master students,the budget here seems to be reasonable. Again, the question is if this will be sufficient to meet the targets on total master students, female master students and regional master students. Please in the narrative give an update on how far you are in reaching this DLI aggregated on national, regional and female students.

I appreciate your comment on the “reasonableness£ of this part of the budget even though now slightly adjusted again.  In the current session we have attracted male regional, and efforts are directed towards addressing the shortfall in the next two academic sessions up until March 2020.Major new budget line without explanation.

- DLI 2.3 PhD students, more or less the same comments as for Master students, with the comment that CEADESE is closer to the target here. Funding for students’ (scholarship/outreach/internships/research/etc) appears many places, it is not possible to get an overview of the total funds allocated per PG student. From a sustainability point of view, the investment per student is important to know for CEADESE moving forward.

In the current session we have attracted female regional, and efforts are directed towards addressing the shortfall in the next two academic sessions up until March 2020, We invest roughly 5,000 USD on every student on the average and this translates to about 50 students in the next two academic sessions.Also, here same type of major new budget line without explanation.

- DLI2.4 Outreach/Internship. This is an area there CEADESE has continued to excel. Budget seems to be to adequate to continue to run this activity within the ACE.

Unfortunately, in the light of the redistribution of funds following funds reduction from CEADESE, and based on your earlier comments that we should adjust the budget based on the reality of funds, we have no choice than to remove the budgetary allocation for this DLI completely, having overshot the budget by the sun of 7,888.15 USD. Its painful that in this areas where CEADESE has been commended, we can no longer continue.You have also exhausted DLR 2.6 still you increase the budget from USD 178,000 to USD 554.358? This seems not to be stringent?

- DLI 2.5 Accreditation seems to be on track. CEADESE awaits feedback from international reviewers’ onsite assessment.

This is notedWhat happened to the cost of accreditation, why did it explode?

- DLI 2.6 Publication. CEADESE has already exhausted all funds to be triggered from delivering this DLI. It is recommended that funds allocated for research should be minimised at this stage to the absolute minimum and any saving made here be allocated towards investing in fund raising.

This has been segregated to include equipment research support in terms of equipment which will also serve as means of fund raising. This argument does not come across clearly in the updated work plan and budget.

- DLI 2.7 Fund raising. With a crude comparison, CEADESE has in the workplan budgeted USD 178,000 for a DLR where there they have reached 100 % and there is no more money to be triggered (DLI 2.6) and USD 24,000 for DLI 2.7 where the latest status update from AAU/WB still indicates 0 % achievement - this seems not a being a very target workplan. Does this represent all the ideas that CEADESE has on how to become financially viable?

This has been addressedHow? Mainly see a budget increasement. The expected increase in IGR requires that all laboratory facilities are up and running and preferably certified, this might take time.

- DLI 2.8 There is allocated USD 360,000 for procurement and infrastructure upgrading. This is a very natural priority at this stage of the project. However, the concern is to what degree the current workplan will trigger sufficient funds to secure this investment.

This has been adjustedYes but the budget for this to some degree to have been moved to other DLR’s like 2.2 and 2.3? As scholarships at the same time has been reduced it is not clear how this reallocation will ensure DLI triggering?

- DLI 3 and 4 CEADESE is preforming average here, but there is still room for improvements. Investment is modest here, no comments.

This is noted