## USES OF FUND AS PER PIM
CENTRE OF EXCELLENCE IN AGRICULTURAL DEVELOPMENT AND SUSTAINABLE ENVIRONMNENT (CEADESE)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT
Uses of Funds by project activities
for the period ending 31st December 2019
(NAIRA)
Expenditure | Semi-Annual Period Between 1st July and 31st December, 2019 |  |  | Cummulative for |  |  | Explanation of | PAD /Life of | Revised
[5 empty] | Financial Year End 31st December, 2019 |  | Variance | Project | PAD
| Actual | Planned @ N305/$ | Variance | Actual | Planned | Variance
Expenditure Classification 1 as per Project Implementation Plan
Cost of running CEADESE office | 606706.18 | 2287500 | 1680793.82 | 1016017.2 | 2287500 | 1271482.8
Cost of stationery and consumables | 477033 | 610000 | 132967 | 559133 | 610000 | 50867
Cost of running Project Vehicle | 148300 | 1830000 | 1681700 | 1087095.22 | 1830000 | 742904.78
Cost of developing Implementation Plan | 0 | 0 | 0 | 0 | 0 | 0
Cost of signing MOUs | 0 | 0 | 0 | 0 | 0 | 0
Cost of adverts/contacts | 0 | 457500 | 457500 | 0 | 457500 | 457500
Operational Cost | 3770100 | 1220000 | -2550100 | 4123500 | 1220000 | -2903500
Cost of coordinating CEADESE meetings | 306495.24 | 915000 | 608504.76 | 558200 | 915000 | 356800
Cost of hosting stakeholders' workshops |  |  | 0 | 0 |  | 0
Cost of attending World Bank meetings and Workshops | 6435000 | 26840000 | 20405000 | 7636125 | 26840000 | 19203875
Cost of training (Management and Faculty) | 8885190 | 30500000 | 21614810 | 15872940 | 30500000 | 14627060
Travels (local & international) | 3658074 | 12200000 | 8541926 | 8039999 | 12200000 | 4160001
Running of CEADESE website | 0 | 244000 | 244000 | 0 | 244000 | 244000
Subscription to Internet and Online journals | 0 | 17635127.45 | 17635127.45 | 18244000 | 17635127.45 | -608872.55
Facilitation of FUNAAB industrial relations | 0 |  | 0 | 0 |  | 0
Cost of Monitoring & Evaluation | 0 |  | 0 | 0 |  | 0
Facilitation of FUNAAB Safeguard office | 0 |  | 0 | 0 |  | 0
Facilitation of FUNAAB Communication Office | 0 | 1220000 | 1220000 | 150000 | 1220000 | 1070000
ADVANCE FROM IGR | 0 |  |  | 0 |  | 0
Sub Total | 24286898.42 | 95959127.45 | 71672229.03 | 57287009.42 | 95959127.45 | 38672118.03
Expenditure Classification 2 as per Project Implementation Plan
Cost of Teaching Materials and softwares | 0 | 7015000 | 7015000 | 0 | 7015000 | 7015000
Cost of Advertisement | 0 | 610000 | 610000 | 0 | 610000 | 610000
Honoraria for Resource persons and Demonstrators | 0 | 10675000 | 10675000 | 0 | 10675000 | 10675000
Operational costs for short term courses | 574000 | 7110364.35 | 6536364.35 | 574000 | 7110364.35 | 6536364.35
Airfare, accommodation, honoraria for facilitors | 0 | 10675000 | 10675000 | 0 | 10675000 | 10675000
Publication of workshop reports | 0 | 1525000 | 1525000 | 0 | 1525000 | 1525000
Cost of running language course M.Agse | 0 | 1525000 | 1525000 | 0 | 1525000 | 1525000
Cost of developing /revising curricula M.Agse | 0 | 1525000 | 1525000 | 0 | 1525000 | 1525000
Payment to adjunct/part time lecturers/visiting professors M.Agse | 0 |  | 0 | 0 |  | 0
Operational Costs M.Agse | 1805679 | 4575000 | 2769321 | 3368799 | 4575000 | 1206201
Cost of Research Consumables, Light Equipment and Accessories (M.Agse) | 56227457.28 | 36149536.35 | -20077920.93 | 56227457.28 | 36149536.35 | -20077920.93
Cost of adverts/contacts | 0 | 1525000 | 1525000 | 0 | 1525000 | 1525000
Cost of course materials M.Agse | 0 |  | 0 | 0 |  | 0
Stationery M.Agse | 0 |  | 0 | 0 |  | 0
Cost of exam materials and invigilation M.Agse | 0 |  | 0 | 0 |  | 0
Cost of scholarship Awards (M.agse) | 0 | 3050000 | 3050000 | 0 | 3050000 | 3050000
Cost of running language course PhD | 246322.5 | 1525000 | 1278677.5 | 246332.5 | 1525000 | 1278667.5
Cost of developing/revising curricula PhD | 0 | 1525000 | 1525000 | 0 | 1525000 | 1525000
Payment to adjunct/part time lecturers/visiting professors PhD | 0 | 0 | 0 | 0 | 0 | 0
Operational Cost Ph.D | 3583860 | 4575000 | 991140 | 4811951.92 | 4575000 | -236951.92
Cost of Research Consumables, Light Equipment and Accessories (PHD) | 9761281.5 | 62104432.45 | 52343150.95 | 9761281.5 | 62104432.45 | 52343150.95
Cost of adverts/contacts PhD | 0 | 1525000 | 1525000 | 0 | 1525000 | 1525000
Cost of course materials PhD | 0 | 0 | 0 | 0 | 0 | 0
Stationery PhD | 0 | 0 | 0 | 0 | 0 | 0
Cost of exam materials and invigilation PhD | 0 | 0 | 0 | 0 | 0 | 0
Cost of scholarship Awards (PhD) | 0 | 6100000 | 6100000 | 0 | 6100000 | 6100000
Travel and Maintenance expenses by M.Agse students | 669992 | 3050000 | 2380008 | 669992 | 3050000 | 2380008
Travel and Maintenance expenses by PhD Agse students | 0 | 3050000 | 3050000 | 0 | 3050000 | 3050000
Travel and Supervision expenses for Faculty | 0 |  | 0 | 0 |  | 0
Operational Cost for outreaches | 102038.08 | 1525000 | 1422961.92 | 1729538.08 | 1525000 | -204538.08
Cost of Stationery | 0 | 3050000 | 3050000 | 0 | 3050000 | 3050000
Meetings | 0 | 12200000 | 12200000 | 0 | 12200000 | 12200000
Printing and Publications | 0 | 15250000 | 15250000 | 0 | 15250000 | 15250000
Publicity | 0 | 7625000 | 7625000 | 0 | 7625000 | 7625000
Administrative Fee for Resource Verification | 0 |  | 0 | 0 |  | 0
National or Regional Accreditation | 0 |  | 0 | 0 |  | 0
International Accreditation | 9869784.75 | 54577410.65 | 44707625.9 | 9941754.75 | 54577410.65 | 44635655.9
Cost of research support | 16864887 | 14954714.25 | -1910172.75 | 21745121.75 | 14954714.25 | -6790407.5
Light Research Equipment | 0 | 138874561.15 | 138874561.15 | 0 | 138874561.15 | 138874561.15
Costs of research theses/dissertations for 30 students | 0 | 3050000 | 3050000 | 0 | 3050000 | 3050000
Costs of publications (page charges) | 0 | 3050000 | 3050000 | 0 | 3050000 | 3050000
Inpur for Externally Generated Revenue | 0 | 53227065.85 | 53227065.85 | 4096500 | 53227065.85 | 49130565.85
Cost of ICT learning platform | 0 |  | 0 | 0 |  | 0
Cost of civil works | 106412977.55 | 5133811.85 | -101279165.7 | 154249170.11 | 5133811.85 | -149115358.26
Cost of equipment and lab purchases | 19478228.89 | 12200000 | -7278228.89 | 84128291.71 | 12200000 | -71928291.71
Establishment of research core facilities | 0 |  | 0 | 0 |  | 0
ADVANCE FROM IGR | 0 |  | 0 | 0 |  | 0
Sub Total | 225596508.55 | 494131896.9 | 268535388.35 | 351550190.6 | 494131896.9 | 142581706.3
Expenditure Classification 3 as per Project Implementation Plan
Cost of Upgrading/running Accounting system | 34285.72 | 549000 | 514714.28 | 360000 | 549000 | 189000
Training of financial Officer in World Bank guidelines and fiduciary methods | 0 | 1525000 | 1525000 | 0 | 1525000 | 1525000
Cost of meetings (audit committees) | 0 | 610000 | 610000 | 0 | 610000 | 610000
Operational Cost | 0 | 610000 | 610000 | 0 | 610000 | 610000
Cost of Training | 598400 | 7534643.75 | 6936243.75 | 598400 | 7534643.75 | 6936243.75
Cost of hiring external auditor | 0 | 1067500 | 1067500 | 0 | 1067500 | 1067500
Cost of auditing accounts | 280000 | 457500 | 177500 | 520000 | 457500 | -62500
Web transparency on financial management (web-access to audit reports, interim financial reports, budgets and annual work-plan) | 0 | 7625000 | 7625000 | 0 | 7625000 | 7625000
ADVANCE FROM IGR | 0 |  | 0 | 0 |  | 0
Sub Total | 912685.72 | 19978643.75 | 19065958.03 | 1478400 | 19978643.75 | 18500243.75
Expenditure Classification 4 as per Project Implementation Plan
Cost of hiring Procurement Consultant |  |  | 0 | 0 |  | 0
Cost of producing procurement manual |  |  | 0 | 0 |  | 0
Cost of producing bid documents | 0 | 610000 | 610000 | 0 | 610000 | 610000
Cost of bid advertisement | 0 | 1525000 | 1525000 | 0 | 1525000 | 1525000
cost of holding bid opening | 0 |  | 0 | 0 |  | 0
Cost of bid evaluation | 0 | 610000 | 610000 | 0 | 610000 | 610000
Operational Cost | 0 | 610000 | 610000 | 0 | 610000 | 610000
Cost of training | 0 | 7667700 | 7667700 | 0 | 7667700 | 7667700
ADVANCE FROM IGR | 0 | 0 | 0 |  | 0 | 0
Sub Total | 0 | 11022700 | 11022700 | 0 | 11022700 | 11022700
Bank Charges | 63269.35 | 0 | -63269.35 | 127609.62 | 0 | -127609.62
Other Expenditure from IGR | 3100000 | 0 | -3100000 | 6510000 | 0 | -6510000
Grand Total Uses of Funds | 253959362.04 | 621092368.1 | 367133006.06 | 416953209.64 | 621092368.1 | 204139158.46
Work on the PAD/Life of project for the period
Grand total of the funds

## SOURCES AND USE OF FUND
CENTRE OF EXCELLENCE IN AGRICULTURAL DEVELOPMENT AND SUSTAINABLE ENVIRONMNENT (CEADESE)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT
Statement of Sources and Uses of Funds
for the Financial Year Ending 31st December , 2019
$1: N305
| Semi-Annual Period from July 1st to December 31st 2019 | Cummulative for
Sources of Fund |  | Financial Period End
2019-12-30
Naira
Opening Cash Balance
Government Funds | 0
TSA Naira Account (project account) | 7334261.28 | 126446041.02
Student Fees and Others (IGR Account Zenith Bank) | 42964028.58 | 45486321.08
Unaab Microfinance Bank | 171247.81 | 171247.81
TSA Dollar Account @ prevailing rate | 396917032.6 | 20122237.75
Total | 447386570.27 | 192225847.66
Add Receipts
Government Funds
World Bank IDA Funds (DISBURSEMENT)
Earned Disbursement for Verified result into TSA Dollar Account @ N305 prevailing rate | 163348993.35 | 459595066.35
Refund | 109292 | 593724.5
Total | 163458285.35 | 460188790.85
Receipt from Other funds
Income from Application fee | 106400 | 1200800
Income from Student fee | 21709800 | 21839800
Income from workshops | 0 | 10000
Income from Laboratory | 157650 | 157650
Other Refunds | 0 | 0
Bidding Fee | 0 | 0
Honorarium | 0 | 0
Total | 21973850 | 23208250
Total Financing | 632818705.62 | 675622888.51
Less: ACE Expenditure as per Project Implementation Plan
DLI1 | 24286898.42 | 57287009.42
DLI2 | 225596508.55 | 351550190.6
DLI3 | 912685.72 | 1478400
DLI4 | 0 | 0
Bank Charges | 57133.1 | 114780.87
Total Uses of Funds by Components | 250853225.79 | 410430380.89
USE OF FUNDS FROM OTHER SOURCES
Payment of first semester Honorarium 2017/2018 Academic session to CEADESE Course lecturers | 3100000 | 6300000
Audit board meeting allowance | 0 | 210000
Bank Charges on IGR Zenith | 5965 | 12657.5
Bank Charges on Unaab Microfinance Bank | 171.25 | 171.25
Total uses of Funds from other funds | 3106136.25 | 6522828.75
GRAND TOTAL | 253959362.04 | 416953209.64
Closing Balances
Government Funds | 0 | 0
Student Fees and Others (IGR Account Zenith Bank) | 51461913.58 | 51461913.58
Unaab Microfinance Bank | 0 | 0
TSA Dollar Account | 120543829.35 | 120543829.35
TSA Naira Account | 115947867.56 | 115947867.56
Total Closing Cash Balance | 287953610.49 | 287953610.49
NOTE: The Zenith Project account has been closed and balance transferred to TSA naira account. However, the TSA naira account is yet to reflect this movement.
The account statement for TSA Dollar account was last received up to 31st july 2018. Consequently, it becomes difficult to reconcile the TSA Dollar account. However a sum of
one hundred and sixty thousand dollars ($160,000)was drawn down from the TSA dollar account to the naira account amounting to fifty two million naira.
The balance of the TSA Naira Account as at 30th June, 2019 was gotten from the university's account officer with the Central Bank of Nigeria but not from the physical bank statement.

## EEP STATEMENT
CENTRE OF EXCELLENCE IN AGRICULTURAL DEVELOPMENT AND SUSTAINABLE ENVIRONMNENT (CEADESE)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (126974)
Statement of Reimbursable Eligible Expenditure Programs (EEPs)
for the semi-annual period ending 30th June, and the Financial Report Ending 31st December, 2019
|  | Cummulative for | Cummulative for
Eligible Expenditure Program (EEP) | Semi-Annual Period ending June 2019 | Financial Period End December 2019 | PAD/Life of Project
Naira
EEP 1: Salaries | 2272922165.02 |  | 4666328847.11
EEP 2: Non Procurable Expenditure as defined in Financing Agreement | 568230541.255 |  | 1166582211.7775
Total EEPs | 2841152706.275 |  | 5832911058.8875
Work on cummulative for the life of project for each Centre

## DLI STATEMENTS
CENTRE OF EXCELLENCE IN AGRICULTURAL DEVELOPMENT AND SUSTAINABLE ENVIRONMNENT (CEADESE)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (126974)
NOTES ANNEX
DISBURSEMENT LINKED TO INDICATORS | ACTIONS TO BE COMPLETED | STATUS OF ACTIONS COMPLETION | AMOUNT ALLOCATED | AMOUNT DISBURSED | UNDISBURSED BALANCE
|  |  | DOLLAR @ N305.00/$ | DOLLAR @ N305.00/$ | DOLLAR @ N305.00/$
DLI1 | Training (Management and Faculty) |  | 314620.09 | 187826.2604 | 126793.8296
DLI2 | Meeting milestones for improved learning and research environment |  | 1620104.58 | 1152623.5757 | 467481.0043
DLI3 | Trainings for Audit committee members |  | 65503.75 | 4847.2131 | 60656.5369
DLI4 | Engagement of Procurement Consultant |  | 36140 | 0 | 36140
TOTAL |  |  | 2036368.42 | 1345297.0492 | 691071.3708
0

## SOURCES & USES OF FUND ANNEX
CENTRE OF EXCELLENCE IN AGRICULTURAL DEVELOPMENT AND SUSTAINABLE ENVIRONMNENT (CEADESE)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT
The schedule below provide additional details on expenditures summarized in the Sources and Uses of Funds covering the period 01-07-2019 to 31-12-2019.
Consultant and Travel Costs
1 |  | Consultant Costs, including project implementation and administration staff | 6300000
2 |  | Travel, Accommodation, and Per Diem | Travel and Accomodation | Per Diem
| i. | International travel | 2989377 | 6435000
| ii. | Domestic travel | 255300 | 413397
|  | Total (Travel, Accommodation, and Per Diem) | 10093074
3 |  | Training and conference fees | 9483590
4 |  | Learning and Research Equipment | 85466967.67
5 |  | Vehicles | 0
6 |  | Other goods incl. reagents | 0
Total Goods and Equipment
Scholarship Payments
7 |  | Scholarship Payments/research support | 16864887
ACE Hosted Workshops and Seminars
8 |  | Workshops and Seminars
Civil Works
9 |  | Civil works, including rehabilitation and new construction | 106412977.55
Marketing, Communication, and Recruitment
10 |  | Communication and Marketing, including website | 0
General Expenses
11 |  | Operating costs including utilities, banking fees etc. | 19337865.82
12 |  | Others
|  | GRAND TOTAL | 253959362.04

## Sheet1
CENTRE OF EXCELLENCE IN AGRICULTURAL DEVELOPMENT AND SUSTAINABLE ENVIRONMNENT (CEADESE)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT
The schedule below provide additional details on expenditures summarized in the Sources and Uses of Funds covering the period 01-01-2018 to 31-12-2018.
Consultant and Travel Costs
1 |  | Consultant Costs, including project implementation and administration staff | 0
2 |  | Travel, Accommodation, and Per Diem | Travel and Accomodation | Per Diem
| i. | International travel | 12718545 | 20210025 | 9640000 | 16482765
| ii. | Domestic travel | 1155895 | 1297620 | 151895 | 331620
|  | Total (Travel, Accommodation, and Per Diem) | 35382085 |  | 26606280
3 |  | Training and conference fees | 15383000 |  | 14473000
Goods and equipment
4 |  | Learning and Research Equipment | 72583910.5 |  | 53363862.5
5 |  | Vehicles | 20704853.63 |  | 3234828.63
6 |  | Other goods incl. reagents | 2005000 |  | 2005000
|  | Total Goods and Equipment | 95293764.13 |  | 58603691.13
Scholarship Payments
7 |  | Scholarship Payments/research support | 16510606.44 |  | 9225038.9
ACE Hosted Workshops and Seminars
8 |  | Workshops and Seminars | 10954100 |  | 10954100
Civil Works
9 |  | Civil works, including rehabilitation and new construction | 154249170.11 |  | 66762208.99
Marketing, Communication, and Recruitment
10 |  | Communication and Marketing, including website | 26000000 |  | 0
General Expenses
11 |  | Operating costs including utilities, banking fees etc. | 7068659.5 |  | 2519520.5
12 |  | Other | 16759839.46 |  | 5987563.03
|  | GRAND TOTAL | 377601224.64 |  | 195131402.55