## USES OF FUND AS PER PIM
CENTRE OF EXCELLENCE IN AGRICULTURAL DEVELOPMENT AND SUSTAINABLE ENVIRONMNENT (CEADESE)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT
Uses of Funds by project activities
for the period ending 30th September 2018
(NAIRA)
Expenditure | Semi-Annual Period ending 30th June, 2018 |  |  | Cummulative for |  |  | Explanation of | PAD /Life of | Revised
[5 empty] | Financial Year End 31st December, 2018 |  | Variance | Project | PAD
| Actual | Planned @ N305/$ | Variance | Actual | Planned | Variance
Expenditure Classification 1 as per Project Implementation Plan
Cost of running CEADESE office | 729540 | 2440000 | 1710460 | 1885270 | 2440000 | 554730
Cost of stationery and consumables | 83400 | 762500 | 679100 | 193900 | 762500 | 568600
Cost of running Project Vehicle | 17671975 | 21480000 | 3808025 | 20574918.63 | 21480000 | 905081.37
Cost of developing Implementation Plan | 0 | 0 | 0 | 0 | 0 | 0
Cost of signing MOUs | 0 | 0 | 0 | 0 | 0 | 0
Cost of adverts/contacts | 0 | 2440000 | 2440000 | 0 | 2440000 | 2440000
Operational Cost | 115650 | 687943.04 | 572293.04 | 215950 | 687943.04 | 471993.04
Cost of coordinating CEADESE meetings | 347895.72 | 1220000 | 872104.28 | 349935.72 | 1220000 | 870064.28
Cost of hosting stakeholders' workshops | 0 | 0 | 0 | 0 | 0 | 0
Cost of attending World Bank meetings and Workshops | 7336105 | 14868750 | 7532645 | 7336105 | 14868750 | 7532645
Cost of training (Management and Faculty) | 2095700 | 91500000 | 89404300 | 2095700 | 91500000 | 89404300
Travels (local & international) | 254000 | 6100000 | 89150300 | 337800 | 6100000 | 5762200 | 83800
Running of CEADESE website | 26000000 | 33184000 | 7184000 | 26000000 | 33184000 | 7184000
Facilitation of FUNAAB industrial relations | 0 | 0 | 0 | 0 | 0 | 0
Cost of Monitoring & Evaluation | 0 | 0 | 0 | 0 | 0 | 0
Facilitation of FUNAAB Safeguard office | 0 | 0 | 0 | 0 | 0 | 0
Facilitation of FUNAAB Communication Office | 0 | 3050000 | 3050000 | 0 | 3050000 | 3050000
ADVANCE FROM IGR | 0 |  | 0 | 0 |  | 0
Sub Total | 54634265.72 | 177733193.04 | 123098927.32 | 58989579.35 | 177733193.04 | 118743613.69
Expenditure Classification 2 as per Project Implementation Plan
Cost of Teaching Materials and softwares | 0 | 2440000 | 2440000 | 0 | 2440000 | 2440000
Cost of Advertisement | 90000 | 1220000 | 1130000 | 90000 | 1220000 | 1130000
Honoraria for Resource persons and Demonstrators | 0 | 0 | 0 | 0 | 0 | 0
Operational costs for workshops | 0 | 4404200 | 4404200 | 1995800 | 4404200 | 2408400
Airfare, accommodation, honoraria for facilitors | 0 | 0 | 0 | 0 | 0 | 0
Publication of workshop reports | 0 | 1220000 | 1220000 | 0 | 1220000 | 1220000
Cost of running language course M.Agse | 0 | 244000 | 244000 | 0 | 244000 | 244000
Cost of developing /revising curricula M.Agse | 0 | 244000 | 244000 | 0 | 244000 | 244000
Payment to adjunct/part time lecturers/visiting professors M.Agse | 0 | 0 | 0 | 0 | 0 | 0
Operational Costs M.Agse | 775980 | 6237128 | 5461148 | 1177580 | 6237128 | 5059548
Cost of adverts/contacts | 0 | 610000 | 610000 | 0 | 610000 | 610000
Cost of course materials M.Agse | 0 | 0 | 0 | 0 | 0 | 0
Stationery M.Agse | 0 | 0 | 0 | 0 | 0 | 0
Cost of exam materials and invigilation M.Agse | 0 | 0 | 0 | 0 | 0 | 0
Cost of scholarship Awards (M.agse) | 0 | 52736000.6 | 52736000.6 | 0 | 52736000.6 | 52736000.6
Cost of running language course PhD | 0 | 244000 | 244000 | 0 | 244000 | 244000
Cost of developing/revising curricula PhD | 0 | 244000 | 244000 | 0 | 244000 | 244000
Payment to adjunct/part time lecturers/visiting professors PhD | 0 | 0 | 0 | 0 | 0 | 0
Operational Cost Ph.D | 598514.28 | 6237128 | 5638613.72 | 1405104.28 | 6237128 | 4832023.72
Cost of adverts/contacts PhD | 0 | 0 | 0 | 0 | 0 | 0
Cost of course materials PhD | 0 | 0 | 0 | 0 | 0 | 0
Stationery PhD | 0 | 0 | 0 | 0 | 0 | 0
Cost of exam materials and invigilation PhD | 0 | 0 | 0 | 0 | 0 | 0
Cost of scholarship Awards (PhD) | 220000 | 14192000 | 13972000 | 220000 | 14192000 | 13972000
Travel and Maintenance expenses by M.Agse students | 0 | 4880000 | 4880000 | 74000 | 4880000 | 4806000
Travel and Maintenance expenses by PhD Agse students |  | 4880000 | 4880000 | 0 | 4880000 | 4880000
Travel and Supervision expenses for Faculty | 0 | 0 | 0 | 0 | 0 | 0
Operational Cost | 1586234 | 8540000 | 6953766 | 2557964 | 8540000 | 5982036
Cost of Stationery | 0 | 244000 | 244000 | 0 | 244000 | 244000
Administrative Fee for Resource Verification | 0 | 0 | 0 | 0 | 0 | 0
National or Regional Accreditation | 0 | 0 | 0 | 0 | 0 | 0
International Accreditation | 1715180 | 21264386.5 | 19549206.5 | 2690630 | 21264386.5 | 18573756.5
Cost of research support | 7065567.54 | 39650000 | 32584432.46 | 10075288.49 | 39650000 | 29574711.51
Costs of research theses/dissertations for 70 students | 0 | 6100000 | 6100000 | 0 | 6100000 | 6100000
Costs of publications (page charges) | 0 | 14640000 | 14640000 | 0 | 14640000 | 14640000
Inpur for Externally Generated Revenue | 0 | 7320000 | 7320000 | 8843550 | 7320000 | -1523550
Cost of ICT learning platform | 0 | 0 | 0 | 0 | 0 | 0
Cost of civil works | 21477837.44 | 122000000 | 100522162.56 | 43965214.01 | 122000000 | 78034785.99
Cost of equipment and lab purchases | 19220048 | 122000000 | 102779952 | 72583910.5 | 122000000 | 49416089.5
Establishment of research core facilities | 0 | 122000000 | 122000000 | 0 | 122000000 | 122000000
ADVANCE FROM IGR | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 52749361.26 | 563790843.1 | 511041481.84 | 145679041.28 | 563790843.1 | 418111801.82
Expenditure Classification 3 as per Project Implementation Plan
Cost of Upgrading/running Accounting system | 0 | 1220000 | 1220000 | 360000 | 1220000 | 860000
Training of financial Officer in World Bank guidelines and fiduciary methods | 0 | 2440000 | 2440000 | 0 | 2440000 | 2440000
Cost of meetings (audit committees) | 0 | 0 | 0 | 0 | 0 | 0
Operational Cost | 0 | 732000 | 732000 | 5200 | 732000 | 726800
Cost of Training | 0 | 0 | 0 | 0 | 0 | 0
Cost of hiring external auditor | 220000 | 732000 | 512000 | 416000 | 732000 | 316000
Cost of auditing accounts | 0 | 488000 | 488000 | 0 | 488000 | 488000
Web transparency on financial management (web-access to audit reports, interim financial reports, budgets and annual work-plan) | 0 | 244000 | 244000 | 0 | 244000 | 244000
ADVANCE FROM IGR | 0 |  | 0 | 0 | 0 | 0
Sub Total | 220000 | 5856000 | 5636000 | 781200 | 5856000 | 5074800
Expenditure Classification 4 as per Project Implementation Plan
Cost of hiring Procurement Consultant | 0 | 0 | 0 | 0 | 0 | 0
Cost of producing procurement manual | 0 | 0 | 0 | 0 | 0 | 0
Cost of producing bid documents | 0 | 0 | 0 | 0 | 0 | 0
Cost of bid advertisement | 1655096.43 | 488000 | -1167096.43 | 1655096.43 | 488000 | -1167096.43
cost of holding bid opening | 0 | 0 | 0 | 0 | 0 | 0
Cost of bid evaluation | 0 | 0 | 0 | 0 | 0 | 0
Operational Cost | 69720 | 524600 | 454880 | 251200 | 524600 | 273400
Cost of training | 0 | 1220000 | 1220000 | 0 | 1220000 | 1220000
ADVANCE FROM IGR | 0 | 0 | 0 | 0 | 0 | 0
Sub Total | 1724816.43 | 2232600 | 507783.57 | 1906296.43 | 2232600 | 326303.57
Bank Charges | 28935 | 0 | -28935 | 40875 | 0 | -40875
Other Expenditure from IGR | 7103320 | 0 | -7103320 | 8729144.5 | 0 | -8729144.5
Grand Total Uses of Funds | 116460698.41 | 749612636.14 | 633151937.73 | 216126136.56 | 749612636.14 | 533486499.58
Work on the PAD/Life of project for the period
Grand total of the funds
NOTE: The N8,843550.00K charged to input for externally generated revenue is in respect of amount of honorarium paid to resource persons for the two international workshops at $19,000 and $10,000 respectively for climate change and e-learning workshops. The relevant exchange rate was $1: N304,95 | [6 empty] | 533486499.58

## SOURCES AND USE OF FUND
CENTRE OF EXCELLENCE IN AGRICULTURAL DEVELOPMENT AND SUSTAINABLE ENVIRONMNENT (CEADESE)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT
Statement of Sources and Uses of Funds
for the period ending 30th September, 2018
| $1:N304.95 | $1:N305.45
Cummulative for
Sources of Fund | Semi-Annual Period ending……30th June 2018 | Financial Period End
2018-09-30
| Naira | Naira
Opening Cash Balance
Government Funds
TSA Naira Account (project account) | 120878416.68 | 120878416.68
World Bank IDA Funds (Project Account Zenith Bank) | 787318.23 | 787318.23
Student Fees and Others (IGR Account Zenith Bank) | 37403216.58 | 37403216.58
Unaab Microfinance Bank | 170113.81 | 170113.81
TSA Dollar Account @ prevailing rate | 18615755.09 | 18646195.25
Total | 177854820.39 | 177885260.55
Add Receipts
Government Funds | 0 | 0
World Bank IDA Funds (DISBURSEMENT)
Earned Disbursement for Verified result into TSA Dollar Account @ prevailing rate | 294867679.06 | 295351147.96
Direct Payment from NUC less Refund | 0 | 0
Refund of unspent advances into TSA Naira project account | 521637 | 521637
CREDIT INTEREST ($991.49 @N305.45K) | 0 | 302850.62
Total | 295389316.06 | 296175635.58
Receipt from Other funds
Income from Application fee | 364800 | 532000
Income from Student fee | 4010000 | 12271800
Income from workshops | 140000 | 1950000
Refund of unspent advances in other payment | 52000 | 52000
Bidding Fee | 710000 | 710000
Honorarium | 0 | 95000
Total | 5276800 | 15610800
Total Financing | 478520936.45 | 489671696.13
Less: ACE Expenditure as per Project Implementation Plan
DLI1 | 54607815.72 | 58989579.35
DLI2 | 52775811.26 | 145679041.28
DLI3 | 220000 | 781200
DLI4 | 1724816.43 | 1906296.43
Bank Charges | 28935 | 40875
Total Uses of Funds by Components | 109357378.41 | 207396992.06
USE OF FUNDS FROM OTHER SOURCES
Payment of first and second semester Honorarium 2016/2017 Academic session to CEADESE Course lecturers | 6700000 | 6895000
refund | 140000 | 140000
payment of shortfall of rent of acccomodation for fadama guys | 42000 | 42000
Audit board meeting allowance | 210000 | 210000
Cost of Repairs and general maintenance | 0 | 607140
refund of students fees | 0 | 650000
refund of workshop fee | 0 | 100000
refund of third party fund on product testing trial | 0 | 28073
refund of bidding fee |  | 40000
Bank Charges on IGR Zenith | 11290 | 16877.5 | 216126136.56
Bank Charges on Unaab Microfinance Bank | 30 | 54
Total uses of Funds from other funds | 7103320 | 8729144.5
GRAND TOTAL | 116460698.41 | 216126136.56
Closing Balances
Government Funds |  |  | 103974.55*305.45
World Bank IDA Funds (Project Account Zenith Bank) | 787318.23 | 0 | 31759026.2975
Student Fees and Others (IGR Account Zenith Bank) | 35536726.58 | 42968126.08
Unaab Microfinance Bank | 170089.81 | 171265.81
TSA Dollar Account | 39028434.15 | 31759026.3
TSA Naira Account | 286424990.93 | 227734654.25
Total Closing Cash Balance | 361947559.7 | 302633072.44
NOTE: The Zenith Project account has been closed and balance transferred to TSA naira account. However, the TSA naira account is yet to reflect this movement.

## EEP STATEMENT
CENTRE OF EXCELLENCE IN AGRICULTURAL DEVELOPMENT AND SUSTAINABLE ENVIRONMNENT (CEADESE)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (126974)
Statement of Reimbursable Eligible Expenditure Programs (EEPs)
for the semi-annual period ending Financial Year End 3oth September, 2018
|  | Cummulative for | Cummulative for
Eligible Expenditure Program (EEP) | Semi-Annual Period ending June 2018 | Financial Period End September 2018 | PAD/Life of Project
Naira
EEP 1: Salaries | 2212998140.02 | 3336735107.1
EEP 2: Non Procurable Expenditure as defined in Financing Agreement | 553249535.005 | 834183776.775
Total EEPs | 2766247675.025 | 4170918883.875
Work on cummulative for the life of project for each Centre

## DLI STATEMENTS
CENTRE OF EXCELLENCE IN AGRICULTURAL DEVELOPMENT AND SUSTAINABLE ENVIRONMNENT (CEADESE)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT (126974)
NOTES ANNEX
DISBURSEMENT LINKED TO INDICATORS | ACTIONS TO BE COMPLETED | STATUS OF ACTIONS COMPLETION | AMOUNT ALLOCATED | AMOUNT DISBURSED | UNDISBURSED BALANCE
|  |  | DOLLAR @ N305.45/$ | DOLLAR @ N305.45/$ | DOLLAR @ N305.45/$
DLI1 | Training (Management and Faculty) | 33.19% | 581873.2789 | 193123.5205 | 388749.7584
DLI2 | Meeting milestones for improved learning and research environment | 25.84% | 1845771.2984 | 476932.53 | 1368838.7684
DLI3 | Trainings for Audit committee members | 13.34% | 19171.7139 | 2557.5381 | 16614.1758
DLI4 | Engagement of Procurement Consultant | 85.38% | 7309.2159 | 6240.9443 | 1068.2716

## SOURCES & USES OF FUND ANNEX
CENTRE OF EXCELLENCE IN AGRICULTURAL DEVELOPMENT AND SUSTAINABLE ENVIRONMNENT (CEADESE)
AFRICA HIGHER EDUCATION CENTERS OF EXCELLENCE PROJECT
The schedule below provide additional details on expenditures summarized in the Sources and Uses of Funds covering the period 01-01-2018 to 30-06-2018.
Consultant and Travel Costs
1 |  | Consultant Costs, including project implementation and administration staff | 0
2 |  | Travel, Accommodation, and Per Diem | Travel and Accomodation | Per Diem
| i. | International travel | 3078545 | 3727260
| ii. | Domestic travel | 371800 | 1682000 |  | 1698000
|  | Total (Travel, Accommodation, and Per Diem) | 8859605 |  |  | 371800
3 |  | Training and conference fees | 910000
Goods and equipment | [5 empty] | 3910999.35
4 |  | Learning and Research Equipment | 72583910.5
5 |  | Vehicles | 19308975 |  |  | 29129916.77
6 |  | Other goods incl. reagents |  |  |  | 20286366.77
|  | Total Goods and Equipment | 91892885.5
Scholarship Payments |  |  |  |  | o/c | 20542766.77
7 |  | Scholarship Payments/research support | 10295288.49 |  | others | 31601888.2
ACE Hosted Workshops and Seminars
8 |  | Workshops and Seminars | 0
Civil Works
9 |  | Civil works, including rehabilitation and new construction | 43965214.01
Marketing, Communication, and Recruitment
10 |  | Communication and Marketing, including website | 26000000
General Expenses
11 |  | Operating costs including utilities, banking fees etc. | 20542766.77
12 |  | Other | 31601888.2
|  | GRAND TOTAL | 234067647.97